## Progress Report
S.No. | TaskName | Assignee | Duration | Start Date (Sch/Actual) | End Date (Sch/Actual) | Delay Days | Total Qty | Progress | % Completion
1 | BASMENT -3 FLOOR PLAN PART -1 & 2 |  | 149 days | 28-Feb-26 / | 26-Jul-26 / | - | 10000% | 9819% | 98.19%
1.1 | UNDERG ROUND PIPE PART-1 & 2 |  | 63 days | 28-Feb-26 / | 01-May-26 / | - | 0% | 15273% | 0%
1.1.1 | TOP PCC WORK PENDNIG |  | 62 days | 28-Feb-26 / | 30-Apr-26 / 08-Apr-26 | - | 24000% | 240 | 100.00%
1.1.2 | PCC BADING |  | 48 days | 15-Mar-26 / | 01-May-26 / 23-Apr-26 | - | 24000% | 24000% | 100.00%
1.1.3 | EXCAVATI ON |  | 1 days | / | / 17-Apr-26 | 45762 | 333 | 333 | 100.00%
1.1.4 | PCC BREAKIN G |  | 1 days | / | / 22-Apr-26 | 45767 | 240 | 240 | 100.00%
1.1.5 | PIPING WORK PART 1 (200 MM PIPE 6KG ASTRAL AQUA SAFE) |  | 1 days | / | / 18-Apr-26 | 45763 | 93.7 | 93.7 | 100.00%
1.1.6 | PIPING WORK PART 1 (BOTTLE GULLY TRAP ASTRAL AQUA SAFE) |  | 1 days | / | / 30-Apr-26 | 45775 | 2 | 2 | 100.00%
1.1.7 | PIPING WORK PART 2 (200 MM PIPE 6KG 6M ASTRAL AQUASAF E) |  | 1 days | / | / 01-May-26 | 45776 | 247 | 247 | 100.00%
1.1.8 | PIPING WORK PART 2 (160 MM PIPE 6KG 6M ASTRAL AQUASAF E) |  | 1 days | / | / 06-May-26 | 45781 | 8.4 | 8.4 | 100.00%
1.1.9 | PIPING WORK PART 2 (BOTTLE GULLY TRAP ASTRAL AQUA SAFE) |  | 1 days | / | / 04-May-26 | 45779 | 5 | 5 | 100.00%
1.2 | BASSMEN T- 1 TO 3 FLOOR DRAIN |  | 62 days | 28-Feb-26 / | 30-Apr-26 / | - | 100 | 97.5 | 97.50%
1.2.1 | FLOOR DRAIN NO - 1 (160 MM) JMR NO: 1 |  | 62 days | 28-Feb-26 / | 30-Apr-26 / 18-Apr-26 | - | 18.6 | 18.6 | 100.00%
1.2.1.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 62 days | 28-Feb-26 / | 30-Apr-26 / 25-Apr-26 | - | 1 | 1 | 100.00%
1.2.2 | FLOOR DRAIN NO - 2 (160 MM) JMR NO: 2 |  | 1 days | / | / 20-Mar-26 | - | 17.2 | 17.2 | 100.00%
1.2.2.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 11-Mar-26 | 45725 | 1 | 1 | 100.00%
1.2.3 | FLOOR DRAIN NO - 3 (160 MM) JMR NO: 3 |  | 1 days | / | / 10-Apr-26 | - | 12.9 | 12.9 | 100.00%
1.2.3.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 18-Apr-26 | 45763 | 1 | 1 | 100.00%
1.2.4 | FLOOR DRAIN NO - 4 (160 MM) JMR NO: 4 |  | 1 days | / | / 17-Apr-26 | - | 17.3 | 17.3 | 100.00%
1.2.4.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 19-Apr-26 | 45764 | 1 | 1 | 100.00%
1.2.5 | FLOOR DRAIN NO - 5 (160 MM) JMR NO: 5 |  | 1 days | / | / 15-Apr-26 | - | 17.3 | 17.3 | 100.00%
1.2.5.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 12-Apr-26 | 45757 | 1 | 1 | 100.00%
1.2.6 | FLOOR DRAIN NO - 6 (160 MM) |  | 1 days | / | / | - | 100 | 0 | 0.00%
1.2.6.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / | 45874 | 1 | 0 | 0.00%
1.2.7 | FLOOR DRAIN NO - 7 (160 MM) JMR NO: 7 |  | 1 days | / | / 01-May-26 | - | 20.7 | 20.7 | 100.00%
1.2.7.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 15-Apr-26 | 45760 | 1 | 1 | 100.00%
1.2.8 | FLOOR DRAIN NO - 8 (160 MM) AC PLANT ROOM |  | 1 days | / | / 01-May-26 | - | 19.6 | 19.6 | 100.00%
1.2.8.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 11-Apr-26 | 45756 | 1 | 1 | 100.00%
1.2.9 | FLOOR DRAIN NO - 9 (160 MM) |  | 1 days | / | / 03-May-26 | - | 10.65 | 10.65 | 100.00%
1.2.9.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 11-Apr-26 | 45756 | 1 | 1 | 100.00%
1.2.10 | FLOOR DRAIN NO - 10 (160 MM) |  | 1 days | / | / 30-Apr-26 | - | 9.65 | 9.65 | 100.00%
1.2.10.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 24-Apr-26 | 45769 | 1 | 1 | 100.00%
1.2.11 | FLOOR DRAIN NO - 11 (160 MM) |  | 1 days | / | / 30-Apr-26 | - | 23 | 23 | 100.00%
1.2.11.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 11-Mar-26 | 45725 | 1 | 1 | 100.00%
1.2.12 | FLOOR DRAIN NO - 12 (160 MM) |  | 1 days | / | / 02-May-26 | - | 10.5 | 10.5 | 100.00%
1.2.12.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 11-Mar-26 | 45725 | 1 | 1 | 100.00%
1.2.13 | FLOOR DRAIN NO - 13 (160 MM) |  | 1 days | / | / 02-May-26 | - | 10.6 | 0 | 0.00%
1.2.13.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / | 45874 | 1 | 0 | 0.00%
1.2.14 | FLOOR DRAIN NO - 14 (160 MM) |  | 1 days | / | / 03-May-26 | - | 10.6 | 10.6 | 100.00%
1.2.14.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 27-Apr-26 | 45772 | 1 | 1 | 100.00%
1.2.15 | FLOOR DRAIN NO - 15 (160 MM) |  | 1 days | / | / 03-May-26 | 45778 | 10.6 | 10.6 | 100.00%
1.2.16 | FLOOR DRAIN NO -16 (160 MM) |  | 1 days | / | / 03-May-26 | 45778 | 10.6 | 10.6 | 100.00%
1.2.17 | Rampe drain chennal floor drain (160 MM) |  | 1 days | / | / 04-May-26 | - | 10.8 | 10.8 | 100.00%
1.2.17.1 | FLOOR DRAIN- CORE 180MM x 175MM |  | 1 days | / | / 24-Apr-26 | 45769 | 1 | 1 | 100.00%
1.2.18 | Pumbing Pump Room drain (160 MM) JMR NO: 6 |  | 1 days | / | / 13-May-26 | 45788 | 24 | 24 | 100.00%
1.2.19 | Rampe drain chennal floor drain (110 MM) |  | 1 days | / | / 20-May-26 | 45795 | 11.2 | 11.2 | 100.00%
1.3 | RAIN WATER SUMP PUMP - 1 |  | 62 days | 28-Feb-26 / | 30-Apr-26 / | - | 100 | 100 | 100.00%
1.3.1 | PUMP DISCHRG E LINE |  | 62 days | 28-Feb-26 / | 30-Apr-26 / | - | 100 | 100 | 100.00%
1.3.1.1 | CORE CUTTING 125MMx1 50MM |  | 62 days | 28-Feb-26 / | 30-Apr-26 / 11-Mar-26 | - | 2 | 2 | 100.00%
1.3.2 | PUMP VENT LINE (110 MM PIPE ASTRAL AQUA SAFE) |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.3.2.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 27-Apr-26 | 45772 | 1 | 1 | 100.00%
1.3.3 | SUMP PUMP FIXING & COMMISN ING |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.3.3.1 | CABLE LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 12-Mar-26 | 45726 | 1 | 1 | 100.00%
1.3.4 | SUMP 1 line (100 MM PIPE SCH-80 ASTRAL CPVC) |  | 1 days | / | / 30-Apr-26 | - | 48.75 | 48.75 | 100.00%
1.3.4.1 | UNDERG ROUNG & FLOOR DRAIN CHANNEL CORE 180MMx1 50MM |  | 1 days | / | / 23-Apr-26 | 45768 | 2 | 2 | 100.00%
1.4 | RAIN WATER SUMP PUMP - 2 |  | 2 days | / | / | - | 100 | 100 | 100.00%
1.4.1 | PUMP DISCHRG E LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.4.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 31-Mar-26 | 45745 | 2 | 2 | 100.00%
1.4.2 | PUMP VENT LINE (110 MM PIPE ASTRAL AQUA SAFE) |  | 1 days | / | / 17-Apr-26 | - | 9.55 | 9.55 | 100.00%
1.4.2.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 10-Apr-26 | 45755 | 1 | 1 | 100.00%
1.4.3 | SUMP PUMP FIXING & COMMISN ING |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.4.3.1 | CABLE LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 01-Jul-26 | 45837 | 1 | 1 | 100.00%
1.4.4 | SUMP 2 line (100 MM PIPE SCH-80 ASTRAL CPVC) |  | 1 days | / | / 30-Apr-26 | - | 17.93 | 17.93 | 100.00%
1.4.4.1 | UNDERG ROUNG FLOOR DRAIN CORE 180MMx1 50MM |  | 1 days | / | / 16-May-26 | 45791 | 3 | 3 | 100.00%
1.5 | RAIN WATER SUMP PUMP - 3 |  | 3 days | / | / | - | 100 | 100 | 100.00%
1.5.1 | PUMP DISCHRG E LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.5.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 08-Apr-26 | 45753 | 2 | 2 | 100.00%
1.5.2 | PUMP VENT LINE (110 MM PIPE ASTRAL AQUA SAFE) |  | 1 days | / | / 21-Apr-26 | - | 10.5 | 10.5 | 100.00%
1.5.2.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 11-Apr-26 | 45756 | 1 | 1 | 100.00%
1.5.3 | SUMP PUMP FIXING & COMMISN ING |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.5.3.1 | CABLE LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 14-Apr-26 | 45759 | 1 | 1 | 100.00%
1.5.4 | SUMP 3 line (100 MM PIPE SCH-80 ASTRAL CPVC) |  | 1 days | / | / 21-Apr-26 | - | 11.35 | 11.35 | 100.00%
1.5.4.1 | UNDERG ROUNG FLOOR DRAIN CORE 180MMx1 50MM |  | 1 days | / | / 10-Apr-26 | 45755 | 1 | 1 | 100.00%
1.5.4.2 | FAIR & PLUMBIN G PUMP RMMOOM CORE CUTTING 180MMx1 50 |  | 1 days | / | / 14-May-26 | 45789 | 1 | 1 | 100.00%
1.6 | SEWER SUMP PUMP |  | 3 days | 22-Apr-26 / | 24-Apr-26 / | - | 100 | 66.667 | 66.67%
1.6.1 | PUMP DISCHRG E LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
1.6.1.1 | Core Cutting 125MMx1 50MM |  | 1 days | / | / 14-Apr-26 | 45759 | 2 | 2 | 100.00%
1.6.2 | PUMP VENT LINE |  | 3 days | / | / | - | 100 | 100 | 100.00%
1.6.2.1 | Core Cutting 125MMx1 50MM |  | 1 days | / | / 11-Apr-26 | 45756 | 1 | 1 | 100.00%
1.6.3 | SUMP PUMP FIXING & COMMISN ING |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
1.6.4 | 100MM PIPE SCH-80 ASTRAL CPVC {SUMP RISER LINE } |  | 3 days | 22-Apr-26 / | 24-Apr-26 / | 105 | 100 | 0 | 0.00%
1.6.5 | WASTE SOIL LINE DOWN TAKE TO SUMP | BHAGHIRATH BHAI | 3 days | / | / | - | 100 | 100 | 100.00%
1.6.5.1 | Core Cutting 125MMx1 50MM | BHAGHIRATH BHAI | 1 days | / | / 23-Apr-26 | 45768 | 2 | 2 | 100.00%
1.6.6 | MUD & GARBAG E LINE COER CUTTING 125MMX1 50MM |  | 1 days | / | / 29-Apr-26 | 45774 | 2 | 2 | 100.00%
1.7 | BASEMEN T - 3 FLOOR PLAN USED FITTINGS PART-2 |  | 1 days | 26-Jul-26 / | 26-Jul-26 / 02-May-26 | - | 100 | 0 | 0.00%
2 | BASSMEN T-3 CELLING PART-1 & 2 | BHARAT BHAI | 1 days | 27-Jul-26 / | 27-Jul-26 / | - | 100 | 50.733 | 50.73%
2.1 | 110 MM ASTRAL SELFIT SWR TYPE-B {VENT LINE} |  | 1 days | 27-Jul-26 / | 27-Jul-26 / 21-Jul-26 | - | 202.93 | 202.93 | 100.00%
2.2 | 160 MM PIPE 6KG ASTRAL AQUASAF E {DRAIN PIPE} |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
2.3 | 160 MM PIPE 6KG ASTRAL AQUASAF E {RAIN WATER PIPE} |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
2.4 | 110 MM PIPE ASTRAL SELFIT SWR TYPE-B {TOILET WASTE LINE} |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
3 | BASSMEN T-2 FLOOR- CELLING PART-1 & 2 |  | 94 days | 14-May-26 / | 15-Aug-26 / | - | 100 | 28.521 | 28.52%
3.1 | COMMON E MALE- FEMALE TOILET |  | 2 days | 14-May-26 / | 15-May-26 / | - | 100 | 119.53 | 119.53%
3.1.1 | COMMON E MALE- FEMALE TOILET DRAINAG E LINE |  | 2 days | 14-May-26 / 13-May-26 | 15-May-26 / 22-May-26 | - | 100 | 139.056 | 139.06%
3.1.1.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | 14-May-26 / 17-May-26 | 14-May-26 / 01-Jun-26 | 18 | 3 | 3 | 100.00%
3.1.1.2 | 50MM PVC SWR TYPE-B SELFIT |  | 2 days | 14-May-26 / 26-May-26 | 15-May-26 / 25-May-26 | 10 | 10.7 | 10.7 | 100.00%
3.1.1.3 | 110MM PVC SWR TYPE-B SELFIT |  | 2 days | 14-May-26 / 24-May-26 | 15-May-26 / 19-May-26 | 4 | 45.1 | 45.1 | 100.00%
3.1.1.4 | 110 X 110MM P- TRAP |  | 2 days | 14-May-26 / 27-May-26 | 15-May-26 / 19-May-26 | 4 | 8 | 8 | 100.00%
3.1.1.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 2 days | 14-May-26 / 25-May-26 | 15-May-26 / 04-Jun-26 | 20 | 3 | 3 | 100.00%
3.1.1.6 | 75MM PVC SWR TYPE-B SELFIT |  | 2 days | 14-May-26 / 24-May-26 | 15-May-26 / 20-May-26 | 5 | 24.92 | 24.92 | 100.00%
3.1.2 | COMMON E MALE TOILET DRAIN LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
3.1.2.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 29-May-26 | 45804 | 2 | 2 | 100.00%
3.1.2.2 | CORE CUTTING 100MMx1 75MM |  | 1 days | / | / 28-May-26 | 45803 | 5 | 5 | 100.00%
3.1.3 | COMMON E FEMALE TOILET DRAIN LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
3.1.3.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 28-May-26 | 45803 | 3 | 3 | 100.00%
3.1.3.2 | CORE CUTTING 100MMx1 75MM |  | 1 days | / | / 28-May-26 | 45803 | 4 | 4 | 100.00%
3.2 | CLUB SIDE DRAIN CHANNEL & FLOOR DRAIN WORK |  | 1 days | / | / | - | 100 | 100 | 100.00%
3.2.1 | CORE CUTTING 180MMx1 50MM |  | 1 days | / | / 28-May-26 | 45803 | 29 | 29 | 100.00%
3.2.2 | RAMP DRAIN CHANNEL CORE CUTTING 180MMx1 50MM |  | 1 days | / | / 03-Jun-26 | 45809 | 1 | 1 | 100.00%
3.3 | RAIN WATER SUMP - 1 |  | 2 days | 29-May-26 / | 30-May-26 / | - | 100 | 100 | 100.00%
3.3.1 | PUMP DISCHAR GE LINE |  | 2 days | 29-May-26 / | 30-May-26 / | - | 100 | 100 | 100.00%
3.3.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 01-Jun-26 | 45807 | 2 | 2 | 100.00%
3.3.1.2 | 100 MM CPVC PIPE SUMP TO CEILING |  | 2 days | 29-May-26 / | 30-May-26 / 04-Jun-26 | 5 | 17.1 | 17.1 | 100.00%
3.4 | RAIN WATER SUMP - 2 |  | 3 days | 01-Jun-26 / | 03-Jun-26 / | - | 100 | 100 | 100.00%
3.4.1 | PUMP DISCHAR GE LINE |  | 3 days | 01-Jun-26 / | 03-Jun-26 / | - | 100 | 100 | 100.00%
3.4.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 01-Jun-26 | 45807 | 2 | 2 | 100.00%
3.4.1.2 | 100 MM CPVC PIPE SUMP TO CEILING |  | 3 days | 01-Jun-26 / | 03-Jun-26 / 04-Jun-26 | 1 | 17.1 | 17.1 | 100.00%
3.5 | RAIN WATER SUMP - 3 |  | 4 days | 01-Jun-26 / | 04-Jun-26 / | - | 100 | 100 | 100.00%
3.5.1 | PUMP DISCHAR GE LINE |  | 4 days | 01-Jun-26 / | 04-Jun-26 / | - | 100 | 100 | 100.00%
3.5.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 01-Jun-26 | 45807 | 2 | 2 | 100.00%
3.5.1.2 | 100 MM CPVC PIPE SUMP TO CEILING |  | 4 days | 01-Jun-26 / | 04-Jun-26 / 04-Jun-26 | - | 17.1 | 17.1 | 100.00%
3.6 | A/C PLANT ROOM FLOOR LINE WORK |  | 3 days | 29-May-26 / | 31-May-26 / | - | 100 | 100 | 100.00%
3.6.1 | CORE CUTTING 180MMx1 75MM |  | 1 days | / | / 05-Jun-26 | 45811 | 1 | 1 | 100.00%
3.6.2 | 160 MM PVC 6KG PIPE |  | 3 days | 29-May-26 / | 31-May-26 / 02-Jun-26 | 2 | 16.45 | 16.45 | 100.00%
3.7 | GARBAG E ROOM LINE |  | 2 days | 28-May-26 / | 29-May-26 / | - | 1 | 1 | 100.00%
3.7.1 | CORE CUTTING 100MMx1 75MM |  | 1 days | / | / 29-May-26 | 45804 | 1 | 1 | 100.00%
3.7.2 | 110 MM PVC 6KG PIPE |  | 2 days | 28-May-26 / | 29-May-26 / 04-Jun-26 | 6 | 5.2 | 5.2 | 100.00%
3.8 | WEEP HOLE LINE 110 MM PIPE PVC 6KG |  | 4 days | 28-May-26 / | 31-May-26 / 30-May-26 | - | 4.35 | 4.35 | 100.00%
3.9 | G.I line piping & Pipe colour work |  | 33 days | 02-Jul-26 / 07-Jul-26 | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
3.10 | Pump room G.I flange installation work |  | 21 days | 26-Jul-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
4 | BASSMEN T-1 FLOOR & CELLING PART-1 & 2 |  | 109 days | 14-May-26 / | 30-Aug-26 / | - | 0 | 0 | 0.00%
4.1 | 160 MM PIPE ASTRAL CPVC SCH-80 {FIRE TANK OVERFLO W} |  | 38 days | 04-Jul-26 / | 10-Aug-26 / | - | 100 | 2.564 | 2.56%
4.1.1 | B-1 & B-2 OVER FLOW TANK CORE CUTTING |  | 1 days | / | / 14-May-26 | 45789 | 1 | 1 | 100.00%
4.1.2 | Sump discharge line piping work | PARESH KUMAR PATEL | 38 days | 04-Jul-26 / 09-Jul-26 | 10-Aug-26 / | - | 100 | 0 | 0.00%
4.2 | 160 MM ASTRAL RING FIT SWR TYPE-B {ALL SHAFT BRANCH CONNEC TION SOIL MAIN HADDER} |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.2.1 | SOIL LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 03-Jul-26 | 45839 | 1 | 1 | 100.00%
4.3 | COMMON E MALE TOILET INTERNA L DRAIN LINE |  | 12 days | 14-May-26 / | 25-May-26 / | - | 100 | 100 | 100.00%
4.3.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 02-Jun-26 | 45808 | 3 | 3 | 100.00%
4.3.2 | CORE CUTTING 100MMx1 75MM |  | 1 days | / | / 02-Jun-26 | 45808 | 5 | 5 | 100.00%
4.3.3 | 50MM PVC SWR TYPE-B SELFIT |  | 2 days | 14-May-26 / | 15-May-26 / 05-Jun-26 | 21 | 7.4 | 7.4 | 100.00%
4.3.4 | 110MM PVC SWR TYPE-B SELFIT |  | 2 days | 24-May-26 / | 25-May-26 / 20-May-26 | - | 6.4 | 6.4 | 100.00%
4.3.5 | 75MM PVC SWR TYPE-B SELFIT |  | 2 days | 24-May-26 / | 25-May-26 / 05-Jun-26 | 11 | 1.85 | 1.85 | 100.00%
4.3.6 | 110 X 110MM P- TRAP |  | 1 days | 24-May-26 / | 24-May-26 / 04-Jun-26 | 11 | 6 | 6 | 100.00%
4.3.7 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | 24-May-26 / | 24-May-26 / 04-Jun-26 | 11 | 2 | 2 | 100.00%
4.4 | COMMON E FEMALE TOILET INTERNA L DRAIN LINE |  | 3 days | 25-May-26 / | 27-May-26 / | - | 100 | 100 | 100.00%
4.4.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 02-Jun-26 | 45808 | 5 | 5 | 100.00%
4.4.2 | CORE CUTTING 100MMx1 75MM |  | 1 days | / | / 02-Jun-26 | 45808 | 3 | 3 | 100.00%
4.4.3 | 50MM PVC SWR TYPE-B SELFIT |  | 2 days | 25-May-26 / | 26-May-26 / 04-Jun-26 | 9 | 3.15 | 3.15 | 100.00%
4.4.4 | 75MM PVC SWR TYPE-B SELFIT |  | 1 days | 25-May-26 / | 25-May-26 / 04-Jun-26 | 10 | 1.5 | 1.5 | 100.00%
4.4.5 | 110MM PVC SWR TYPE-B SELFIT |  | 2 days | 26-May-26 / | 27-May-26 / 04-Jun-26 | 8 | 2.3 | 2.3 | 100.00%
4.4.6 | 110 X 110MM P- TRAP |  | 1 days | 25-May-26 / | 25-May-26 / 04-Jun-26 | 10 | 4 | 4 | 100.00%
4.4.7 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | 26-May-26 / | 26-May-26 / 04-Jun-26 | 9 | 1 | 1 | 100.00%
4.5 | TANKER INLET |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.5.1 | TANKER LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 05-Jun-26 | 45811 | 1 | 1 | 100.00%
4.5.2 | TANKER FILL UP LINE CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 06-Jun-26 | 45812 | 2 | 2 | 100.00%
4.6 | RAIN WATER SUMP - 1, B-1 |  | 2 days | 01-Jul-26 / | 02-Jul-26 / | - | 100 | 100 | 100.00%
4.6.1 | PUMP DISCHAR GE LINE |  | 2 days | 01-Jul-26 / | 02-Jul-26 / | - | 100 | 100 | 100.00%
4.6.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 05-Jun-26 | 45811 | 2 | 2 | 100.00%
4.6.1.2 | 100 MM CPVC SUMP LINE |  | 2 days | 01-Jul-26 / 01-Jul-26 | 02-Jul-26 / 02-Jul-26 | - | 173 | 173 | 100.00%
4.7 | RAIN WATER SUMP - 2 |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.7.1 | PUMP DISCHAR GE LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.7.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 05-Jun-26 | 45811 | 2 | 2 | 100.00%
4.8 | RAIN WATER SUMP - 3 |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.8.1 | PUMP DISCHAR GE LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.8.1.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 05-Jun-26 | 45811 | 2 | 2 | 100.00%
4.9 | A/C PLANT ROOM |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.9.1 | DRAIN CHANNEL CORE 180MMx1 75MM |  | 1 days | / | / 06-Jun-26 | 45812 | 1 | 1 | 100.00%
4.10 | GARBAG E ROOM |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.10.1 | CORE CUTTING 125MMx1 50MM |  | 1 days | / | / 06-Jun-26 | 45812 | 1 | 1 | 100.00%
4.11 | DWS/FWS LINE |  | 1 days | / | / | - | 100 | 100 | 100.00%
4.11.1 | WATER SUPPLY RISUR G.I LINE 100MMx1 75MM |  | 1 days | / | / 06-Jun-26 | 45812 | 2 | 2 | 100.00%
4.11.2 | DWS/FWS TOILET CORE 100MMx1 75MM |  | 1 days | / | / 06-Jun-26 | 45812 | 2 | 2 | 100.00%
4.12 | 100 MM CPVC TUNNEL LINE |  | 9 days | 24-Jun-26 / | 02-Jul-26 / 02-Jul-26 | - | 61 | 61 | 100.00%
4.13 | 40 MM CPVC DOMESTI C & FLUSHIN G |  | 1 days | 01-Jul-26 / | 01-Jul-26 / 01-Jul-26 | - | 49.1 | 49.1 | 100.00%
4.14 | KHURRA FIXING |  | 2 days | 29-Jul-26 / 29-Jul-26 | 30-Jul-26 / 30-Jul-26 | - | 100 | 100 | 100.00%
4.15 | 250 MM PIPE DRAINAG E LINE HANGING | PARESH KUMAR PATEL | 32 days | 30-Jul-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
4.16 | 110 MM AC DRAIN LINE HANGING | PARESH KUMAR PATEL | 19 days | 28-Jul-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
4.17 | 100 MM MOTORSI ZED VALVE FIXING TUNNEL LINE | PARESH KUMAR PATEL | 8 days | 22-Aug-26 / | 29-Aug-26 / | - | 100 | 0 | 0.00%
4.18 | 100 MM WEEP HOLE LINE PIPE HANGING | PARESH KUMAR PATEL | 15 days | 09-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
4.19 | 110 MM SUB-SOIL LINE PIPE HANGING | PARESH KUMAR PATEL | 15 days | 09-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
4.20 | RWP SUMP NO -2 & 3 DISCHAR GE LINE HANGING | PARESH KUMAR PATEL | 15 days | 04-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
5 | 1ST FLOOR |  | 93 days | 03-Jun-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.1 | 1ST FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | - | 100 | 0 | 0.00%
5.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 10-Jun-26 | 45816 | 100 | 0 | 0.00%
5.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 08-Jun-26 | 45814 | 100 | 0 | 0.00%
5.1.3 | 25 Mm Ball Valve |  | 1 days | / | / | 45874 | 8 | 0 | 0.00%
5.2 | 1ST FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 10 days | 03-Jun-26 / | 12-Jun-26 / | - | 100 | 95.15 | 95.15%
5.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | 12-Jun-26 / | 12-Jun-26 / 08-Jun-26 | - | 12.7 | 12.7 | 100.00%
5.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 8 days | 03-Jun-26 / | 10-Jun-26 / 08-Jun-26 | - | 93.28 | 93.28 | 100.00%
5.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 8 days | 03-Jun-26 / | 10-Jun-26 / 08-Jun-26 | - | 2.2 | 2.2 | 100.00%
5.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 08-Jun-26 | 45814 | 8 | 8 | 100.00%
5.3 | 1ST FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE | PRAFULLA MALIK, SATYARANJAN MALIK | 1 days | / | / | - | 100 | 0 | 0.00%
5.3.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
5.3.2 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
5.3.3 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 25-Mar-26 | 45739 | 0 | 5 | 0.00%
5.3.4 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK, SATYARANJAN MALIK | 1 days | / | / 25-Mar-26 | 45739 | 0 | 17 | 0.00%
5.4 | 1ST FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / 26-Mar-26 | - | 100 | 0 | 0.00%
5.4.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
5.4.2 | 110 X 110MM P- TRAP |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
5.4.3 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
5.4.4 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 23-Mar-26 | 45737 | 0 | 5 | 0.00%
5.4.5 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 25-Mar-26 | 45739 | 0 | 17 | 0.00%
5.5 | 1ST FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 01-Sep-26 / | 03-Sep-26 / | - | 100 | 0 | 0.00%
5.5.1 | WATER CLOSET |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.3 | HEALTH FAUCET |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.4 | TWO WAY BIB COCK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.5 | TWIN ROBE HOOK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.6 | TOILET PAPER HOLDER |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.5.7 | WASH BASIN |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.5.9 | ANGLE VALVE |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.5.11 | URINAL BASIN |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.5.13 | SOAP DISPENS ER |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.6 | 1ST FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 01-Sep-26 / | 03-Sep-26 / | - | 100 | 0 | 0.00%
5.6.1 | WATER CLOSET |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.3 | HEALTH FAUCET |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.4 | TWO WAY BIB COCK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.5 | TWIN ROBE HOOK |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.6 | TOILET PAPER HOLDER |  | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 0 | 0 | 0.00%
5.6.7 | WASH BASIN |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.6.9 | ANGLE VALVE |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 0 | 0 | 0.00%
5.6.11 | URINAL BASIN |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.6.13 | SOAP DISPENS ER |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 0 | 0 | 0.00%
5.7 | 1ST FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
5.8 | 1ST FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
6 | 2ND FLOOR |  | 162 days | 29-Mar-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.1 | 2ND FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 25-May-26 / | 30-May-26 / | - | 100 | 71.097 | 71.10%
6.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 25-May-26 / 28-May-26 | 30-May-26 / 26-May-26 | - | 12.7 | 12.7 | 100.00%
6.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 3 days | 25-May-26 / 15-May-26 | 27-May-26 / 30-May-26 | 3 | 93.28 | 93.28 | 100.00%
6.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 25-May-26 / 25-May-26 | 30-May-26 / 30-May-26 | - | 2.2 | 2.2 | 100.00%
6.1.4 | 25 Mm Ball Valve |  | 6 days | 25-May-26 / | 30-May-26 / 30-May-26 | - | 8 | 8 | 100.00%
6.2 | 2ND FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 38 days | 25-Apr-26 / | 01-Jun-26 / | - | 100 | 100 | 100.00%
6.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 8 days | 25-May-26 / | 01-Jun-26 / 24-May-26 | - | 29.57 | 29.57 | 100.00%
6.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 25-Apr-26 / | 01-May-26 / 24-May-26 | 23 | 89.2 | 89.2 | 100.00%
6.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 25-Apr-26 / | 01-May-26 / 01-May-26 | - | 2.2 | 2.2 | 100.00%
6.2.4 | 25 Mm Ball Valve |  | 7 days | 25-Apr-26 / | 01-May-26 / 01-May-26 | - | 8 | 8 | 100.00%
6.3 | 2ND FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 63 days | 29-Mar-26 / | 30-May-26 / | - | 100 | 68 | 68.00%
6.3.1 | 110MM PVC CLEANOU T PLUG |  | 7 days | 29-Mar-26 / 29-Mar-26 | 04-Apr-26 / 02-Apr-26 | - | 4 | 4 | 100.00%
6.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 7 days | 29-Mar-26 / | 04-Apr-26 / 30-May-26 | 56 | 12.8 | 12.8 | 100.00%
6.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 3 days | 28-May-26 / | 30-May-26 / 30-May-26 | - | 51.7 | 51.7 | 100.00%
6.3.4 | 110 X 110MM P- TRAP |  | 3 days | 28-May-26 / | 30-May-26 / 30-May-26 | - | 9 | 9 | 100.00%
6.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 3 days | 28-May-26 / | 30-May-26 / 30-May-26 | - | 5 | 5 | 100.00%
6.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 02-Apr-26 | 45747 | 0 | 5 | 0.00%
6.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 02-Apr-26 | 45747 | 0 | 17 | 0.00%
6.4 | 2ND FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 29-Mar-26 / | 08-Apr-26 / | - | 100 | 55.731 | 55.73%
6.4.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | / | / 02-Apr-26 | 45747 | 4 | 4 | 100.00%
6.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 11 days | 29-Mar-26 / | 08-Apr-26 / 02-Apr-26 | - | 12.3 | 12.3 | 100.00%
6.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 02-Apr-26 | 45747 | 43.36 | 43.36 | 100.00%
6.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 02-Apr-26 | 45747 | 9 | 9 | 100.00%
6.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 02-Apr-26 | 45747 | 5 | 5 | 100.00%
6.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 02-Apr-26 | 45747 | 5 | 5 | 100.00%
6.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 02-Apr-26 | 45747 | 17 | 17 | 100.00%
6.5 | 2ND FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
6.5.1 | WATER CLOSET |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.3 | HEALTH FAUCET |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.4 | TWO WAY BIB COCK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.5 | TWIN ROBE HOOK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.6 | TOILET PAPER HOLDER |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.5.7 | WASH BASIN |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.5.9 | ANGLE VALVE |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.5.11 | URINAL BASIN |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.5.13 | SOAP DISPENS ER |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.6 | 2ND FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
6.6.1 | WATER CLOSET |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.3 | HEALTH FAUCET |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.4 | TWO WAY BIB COCK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.5 | TWIN ROBE HOOK |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.6 | TOILET PAPER HOLDER |  | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 0 | 0 | 0.00%
6.6.7 | WASH BASIN |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.6.9 | ANGLE VALVE |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 0 | 0 | 0.00%
6.6.11 | URINAL BASIN |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.6.13 | SOAP DISPENS ER |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 0 | 0 | 0.00%
6.7 | 2ND FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
6.8 | 2ND FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
7 | 3RD FLOOR |  | 172 days | 22-Mar-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.1 | 3RD FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 28 days | 22-Mar-26 / | 18-Apr-26 / | - | 100 | 108.029 | 108.03%
7.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 28 days | 22-Mar-26 / | 18-Apr-26 / 18-Apr-26 | - | 12.7 | 12.7 | 100.00%
7.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 14-Apr-26 / | 18-Apr-26 / 18-Apr-26 | - | 93.28 | 93.28 | 100.00%
7.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 18-Apr-26 | 45763 | 2.2 | 2.2 | 100.00%
7.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 18-Apr-26 | 45763 | 8 | 8 | 100.00%
7.2 | 3RD FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 10 days | 15-May-26 / | 24-May-26 / | - | 100 | 169.795 | 169.79%
7.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 10 days | 15-May-26 / | 24-May-26 / 24-May-26 | - | 29.57 | 29.57 | 100.00%
7.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 10 days | 15-May-26 / | 24-May-26 / 24-May-26 | - | 89.2 | 89.2 | 100.00%
7.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 24-May-26 | 45799 | 2.2 | 2.2 | 100.00%
7.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 24-May-26 | 45799 | 8 | 8 | 100.00%
7.3 | 3RD FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 28 days | 22-Mar-26 / | 18-Apr-26 / | - | 100 | 16.159 | 16.16%
7.3.1 | 110MM PVC CLEANOU T PLUG |  | 28 days | 22-Mar-26 / | 18-Apr-26 / 24-Mar-26 | - | 4 | 4 | 100.00%
7.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 3 days | 22-Mar-26 / | 24-Mar-26 / 24-Mar-26 | - | 12.8 | 12.8 | 100.00%
7.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 3 days | 22-Mar-26 / | 24-Mar-26 / 24-Mar-26 | - | 51.7 | 51.7 | 100.00%
7.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 24-Mar-26 | 45738 | 9 | 9 | 100.00%
7.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 24-Mar-26 | 45738 | 5 | 5 | 100.00%
7.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 24-Mar-26 | 45738 | 5 | 5 | 100.00%
7.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 24-Mar-26 | 45738 | 17 | 17 | 100.00%
7.4 | 3RD FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 28 days | 26-Mar-26 / | 22-Apr-26 / | - | 100 | 23.468 | 23.47%
7.4.1 | 110MM PVC CLEANOU T PLUG |  | 28 days | 26-Mar-26 / | 22-Apr-26 / 30-Mar-26 | - | 4 | 4 | 100.00%
7.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 5 days | 26-Mar-26 / | 30-Mar-26 / 30-Mar-26 | - | 14.55 | 14.55 | 100.00%
7.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 5 days | 26-Mar-26 / | 30-Mar-26 / 30-Mar-26 | - | 51.98 | 51.98 | 100.00%
7.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 30-Mar-26 | 45744 | 9 | 9 | 100.00%
7.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 30-Mar-26 | 45744 | 5 | 5 | 100.00%
7.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 30-Mar-26 | 45744 | 5 | 5 | 100.00%
7.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 30-Mar-26 | 45744 | 17 | 17 | 100.00%
7.5 | 3RD FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 07-Sep-26 / | 09-Sep-26 / | - | 100 | 0 | 0.00%
7.5.1 | WATER CLOSET |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.3 | HEALTH FAUCET |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.4 | TWO WAY BIB COCK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.5 | TWIN ROBE HOOK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.6 | TOILET PAPER HOLDER |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.5.7 | WASH BASIN |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.5.9 | ANGLE VALVE |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.5.11 | URINAL BASIN |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.5.13 | SOAP DISPENS ER |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.6 | 3RD FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 07-Sep-26 / | 09-Sep-26 / | - | 100 | 0 | 0.00%
7.6.1 | WATER CLOSET |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.3 | HEALTH FAUCET |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.4 | TWO WAY BIB COCK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.5 | TWIN ROBE HOOK |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.6 | TOILET PAPER HOLDER |  | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 0 | 0 | 0.00%
7.6.7 | WASH BASIN |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.6.9 | ANGLE VALVE |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 0 | 0 | 0.00%
7.6.11 | URINAL BASIN |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.6.13 | SOAP DISPENS ER |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 0 | 0 | 0.00%
7.7 | 3RD FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
7.8 | 3RD FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
8 | 4TH FLOOR |  | 173 days | 24-Mar-26 / | 12-Sep-26 / | - | 100 | 49.166 | 49.17%
8.1 | 4TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 17-Apr-26 / | 21-Apr-26 / | - | 100 | 90.738 | 90.74%
8.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | DOODHNATH JAISWAL | 5 days | 17-Apr-26 / 16-Jul-26 | 21-Apr-26 / 24-Apr-26 | 3 | 12.7 | 12.7 | 100.00%
8.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 17-Apr-26 / | 21-Apr-26 / 21-Apr-26 | - | 93.28 | 93.28 | 100.00%
8.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 21-Apr-26 | 45766 | 2.2 | 2.2 | 100.00%
8.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 21-Apr-26 | 45766 | 8 | 8 | 100.00%
8.2 | 4TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 41 days | 15-May-26 / | 24-Jun-26 / | - | 100 | 95.355 | 95.36%
8.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 41 days | 15-May-26 / | 24-Jun-26 / 26-May-26 | - | 29.57 | 29.57 | 100.00%
8.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 10 days | 15-May-26 / | 24-May-26 / 26-May-26 | 2 | 89.2 | 89.2 | 100.00%
8.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 26-May-26 | 45801 | 2.2 | 2.2 | 100.00%
8.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 26-May-26 | 45801 | 8 | 8 | 100.00%
8.3 | 4TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 29 days | 24-Mar-26 / | 21-Apr-26 / | - | 100 | 19.969 | 19.97%
8.3.1 | 110MM PVC CLEANOU T PLUG |  | 29 days | 24-Mar-26 / | 21-Apr-26 / 27-Mar-26 | - | 4 | 4 | 100.00%
8.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 4 days | 24-Mar-26 / | 27-Mar-26 / 27-Mar-26 | - | 12.8 | 12.8 | 100.00%
8.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 4 days | 24-Mar-26 / | 27-Mar-26 / 27-Mar-26 | - | 51.7 | 51.7 | 100.00%
8.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 27-Mar-26 | 45741 | 9 | 9 | 100.00%
8.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 27-Feb-26 | 45713 | 5 | 5 | 100.00%
8.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 27-Mar-26 | 45741 | 5 | 5 | 100.00%
8.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 27-Mar-26 | 45741 | 17 | 17 | 100.00%
8.4 | 4TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 44 days | 02-Apr-26 / | 15-May-26 / | - | 100 | 29.592 | 29.59%
8.4.1 | 110MM PVC CLEANOU T PLUG |  | 44 days | 02-Apr-26 / | 15-May-26 / 10-Apr-26 | - | 4 | 4 | 100.00%
8.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 9 days | 02-Apr-26 / | 10-Apr-26 / 10-Apr-26 | - | 14.55 | 14.55 | 100.00%
8.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 9 days | 02-Apr-26 / | 10-Apr-26 / 10-Apr-26 | - | 51.98 | 51.98 | 100.00%
8.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 10-Apr-26 | 45755 | 9 | 9 | 100.00%
8.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 10-Apr-26 | 45755 | 5 | 5 | 100.00%
8.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 10-Apr-26 | 45755 | 5 | 5 | 100.00%
8.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 10-Apr-26 | 45755 | 17 | 17 | 100.00%
8.5 | 4TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 10-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
8.5.1 | WATER CLOSET |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.3 | HEALTH FAUCET |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.4 | TWO WAY BIB COCK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.5 | TWIN ROBE HOOK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.6 | TOILET PAPER HOLDER |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.5.7 | WASH BASIN |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.5.9 | ANGLE VALVE |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.5.11 | URINAL BASIN |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.5.13 | SOAP DISPENS ER |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.6 | 4TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 10-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
8.6.1 | WATER CLOSET |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.3 | HEALTH FAUCET |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.4 | TWO WAY BIB COCK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.5 | TWIN ROBE HOOK |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.6 | TOILET PAPER HOLDER |  | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 0 | 0 | 0.00%
8.6.7 | WASH BASIN |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.6.9 | ANGLE VALVE |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 0 | 0 | 0.00%
8.6.11 | URINAL BASIN |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.6.13 | SOAP DISPENS ER |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 0 | 0 | 0.00%
8.7 | 4TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
8.8 | 4TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
9 | 5TH FLOOR |  | 173 days | 27-Mar-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.1 | 5TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 25-Apr-26 / | 30-Apr-26 / | - | 100 | 93.014 | 93.01%
9.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 25-Apr-26 / | 30-Apr-26 / 30-Apr-26 | - | 12.7 | 12.7 | 100.00%
9.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 25-Apr-26 / | 30-Apr-26 / 30-Apr-26 | - | 93.28 | 93.28 | 100.00%
9.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 30-Apr-26 | 45775 | 2.2 | 2.2 | 100.00%
9.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 30-Apr-26 | 45775 | 8 | 8 | 100.00%
9.2 | 5TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 54 days | 05-Apr-26 / | 28-May-26 / | - | 100 | 95.894 | 95.89%
9.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 54 days | 05-Apr-26 / | 28-May-26 / 16-May-26 | - | 29.57 | 29.57 | 100.00%
9.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 10-May-26 / | 15-May-26 / 16-May-26 | 1 | 89.2 | 89.2 | 100.00%
9.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 16-May-26 | 45791 | 2.2 | 2.2 | 100.00%
9.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 30-May-26 | 45805 | 8 | 8 | 100.00%
9.3 | 5TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 35 days | 27-Mar-26 / | 30-Apr-26 / | - | 100 | 0 | 0.00%
9.3.1 | 110MM PVC CLEANOU T PLUG |  | 35 days | 27-Mar-26 / | 30-Apr-26 / 30-Mar-26 | - | 0 | 4 | 0.00%
9.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 4 days | 27-Mar-26 / | 30-Mar-26 / 30-Mar-26 | - | 12.8 | 12.8 | 100.00%
9.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 4 days | 27-Mar-26 / | 30-Mar-26 / 30-Mar-26 | - | 51.7 | 51.7 | 100.00%
9.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 30-Mar-26 | 45744 | 0 | 9 | 0.00%
9.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 30-Mar-26 | 45744 | 0 | 5 | 0.00%
9.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 30-Mar-26 | 45744 | 0 | 5 | 0.00%
9.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 30-Mar-26 | 45744 | 0 | 17 | 0.00%
9.4 | 5TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 57 days | 02-Apr-26 / | 28-May-26 / | - | 100 | 13.235 | 13.23%
9.4.1 | 110MM PVC CLEANOU T PLUG |  | 54 days | 05-Apr-26 / | 28-May-26 / 10-Apr-26 | - | 0 | 4 | 0.00%
9.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 10-Apr-26 | 45755 | 0 | 14.55 | 0.00%
9.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 9 days | 02-Apr-26 / | 10-Apr-26 / 10-Apr-26 | - | 51.98 | 51.98 | 100.00%
9.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 10-Apr-26 | 45755 | 0 | 9 | 0.00%
9.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 10-Apr-26 | 45755 | 0 | 5 | 0.00%
9.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 10-Apr-26 | 45755 | 0 | 5 | 0.00%
9.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 10-Apr-26 | 45755 | 0 | 17 | 0.00%
9.5 | 5TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 13-Sep-26 / | 15-Sep-26 / | - | 100 | 0 | 0.00%
9.5.1 | WATER CLOSET |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.3 | HEALTH FAUCET |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.4 | TWO WAY BIB COCK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.5 | TWIN ROBE HOOK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.6 | TOILET PAPER HOLDER |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.5.7 | WASH BASIN |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.5.9 | ANGLE VALVE |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.5.11 | URINAL BASIN |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.5.13 | SOAP DISPENS ER |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.6 | 5TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 13-Sep-26 / | 15-Sep-26 / | - | 100 | 0 | 0.00%
9.6.1 | WATER CLOSET |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.3 | HEALTH FAUCET |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.4 | TWO WAY BIB COCK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.5 | TWIN ROBE HOOK |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.6 | TOILET PAPER HOLDER |  | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 0 | 0 | 0.00%
9.6.7 | WASH BASIN |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.6.9 | ANGLE VALVE |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 14-Sep-26 / | 14-Sep-26 / | - | 0 | 0 | 0.00%
9.6.11 | URINAL BASIN |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.6.13 | SOAP DISPENS ER |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
9.7 | 5TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
9.8 | 5TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
10 | 6TH FLOOR |  | 175 days | 28-Mar-26 / | 18-Sep-26 / | - | 0 | 0 | 0.00%
10.1 | 6TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 08-May-26 / | 13-May-26 / | - | 100 | 93.184 | 93.18%
10.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 08-May-26 / | 13-May-26 / 13-May-26 | - | 12.7 | 12.7 | 100.00%
10.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 08-May-26 / | 13-May-26 / 13-May-26 | - | 93.28 | 93.28 | 100.00%
10.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 13-May-26 | 45788 | 2.2 | 2.2 | 100.00%
10.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 13-May-26 | 45788 | 8 | 8 | 100.00%
10.2 | 6TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 08-May-26 / | 13-May-26 / | - | 100 | 171.524 | 171.52%
10.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 08-May-26 / | 13-May-26 / 29-May-26 | 16 | 29.57 | 29.57 | 100.00%
10.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 08-May-26 / | 13-May-26 / 29-May-26 | 16 | 89.2 | 89.2 | 100.00%
10.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 29-May-26 | 45804 | 2.2 | 2.2 | 100.00%
10.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 29-May-26 | 45804 | 8 | 8 | 100.00%
10.3 | 6TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 7 days | 28-Mar-26 / | 03-Apr-26 / | - | 100 | 37.133 | 37.13%
10.3.1 | 110MM PVC CLEANOU T PLUG |  | 7 days | 28-Mar-26 / | 03-Apr-26 / 03-Apr-26 | - | 4 | 4 | 100.00%
10.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 7 days | 28-Mar-26 / | 03-Apr-26 / 03-Apr-26 | - | 12.8 | 12.8 | 100.00%
10.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 03-Apr-26 | 45748 | 51.7 | 51.7 | 100.00%
10.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 03-Apr-26 | 45748 | 9 | 9 | 100.00%
10.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 03-Apr-26 | 45748 | 5 | 5 | 100.00%
10.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 03-Apr-26 | 45748 | 5 | 5 | 100.00%
10.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 03-Apr-26 | 45748 | 17 | 17 | 100.00%
10.4 | 6TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 37 days | 08-Apr-26 / | 14-May-26 / | - | 100 | 19.474 | 19.47%
10.4.1 | 110MM PVC CLEANOU T PLUG |  | 5 days | 08-Apr-26 / | 12-Apr-26 / 12-Apr-26 | - | 4 | 4 | 100.00%
10.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | 14-May-26 / | 14-May-26 / 12-Apr-26 | - | 14.55 | 14.55 | 100.00%
10.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | 13-May-26 / | 13-May-26 / 12-Apr-26 | - | 51.98 | 51.98 | 100.00%
10.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 12-Apr-26 | 45757 | 9 | 9 | 100.00%
10.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 12-Apr-26 | 45757 | 5 | 5 | 100.00%
10.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 12-Apr-26 | 45757 | 5 | 5 | 100.00%
10.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 12-Apr-26 | 45757 | 17 | 17 | 100.00%
10.5 | 6TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 16-Sep-26 / | 18-Sep-26 / | - | 100 | 0 | 0.00%
10.5.1 | WATER CLOSET |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.3 | HEALTH FAUCET |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.4 | TWO WAY BIB COCK |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.5 | TWIN ROBE HOOK |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.6 | TOILET PAPER HOLDER |  | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 0 | 0 | 0.00%
10.5.7 | WASH BASIN |  | 1 days | 17-Sep-26 / | 17-Sep-26 / | - | 0 | 0 | 0.00%
10.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 17-Sep-26 / | 17-Sep-26 / | - | 0 | 0 | 0.00%
10.5.9 | ANGLE VALVE |  | 1 days | 17-Sep-26 / | 17-Sep-26 / | - | 0 | 0 | 0.00%
10.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 17-Sep-26 / | 17-Sep-26 / | - | 0 | 0 | 0.00%
10.5.11 | URINAL BASIN |  | 1 days | 18-Sep-26 / | 18-Sep-26 / | - | 0 | 0 | 0.00%
10.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 18-Sep-26 / | 18-Sep-26 / | - | 0 | 0 | 0.00%
10.5.13 | SOAP DISPENS ER |  | 1 days | 18-Sep-26 / | 18-Sep-26 / | - | 0 | 0 | 0.00%
10.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 18-Sep-26 / | 18-Sep-26 / | - | 0 | 0 | 0.00%
10.6 | 6TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | - | 100 | 0 | 0.00%
10.6.1 | WATER CLOSET |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.3 | HEALTH FAUCET |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.4 | TWO WAY BIB COCK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.5 | TWIN ROBE HOOK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.6 | TOILET PAPER HOLDER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.7 | WASH BASIN |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.9 | ANGLE VALVE |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.11 | URINAL BASIN |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.13 | SOAP DISPENS ER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.6.14 | SS SINGLE PIECE GRATING |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
10.7 | 6TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
10.8 | 6TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
11 | 7TH FLOOR |  | 171 days | 04-Apr-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.1 | 7TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 45 days | 04-Apr-26 / 12-Jun-26 | 18-May-26 / 19-Jun-26 | - | 100 | 101.295 | 101.30%
11.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 12-May-26 / | 18-May-26 / 09-Apr-26 | - | 12.7 | 12.7 | 100.00%
11.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 6 days | 04-Apr-26 / | 09-Apr-26 / 09-Apr-26 | - | 93.28 | 93.28 | 100.00%
11.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 09-Apr-26 | 45754 | 2.2 | 2.2 | 100.00%
11.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 09-Apr-26 | 45754 | 8 | 8 | 100.00%
11.2 | 7TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / 12-Jun-26 | / 25-Jun-26 | - | 100 | 100 | 100.00%
11.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 17-Jun-26 | 45823 | 10.85 | 10.85 | 100.00%
11.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 19-Jun-26 | 45825 | 94.53 | 94.53 | 100.00%
11.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 19-Jun-26 | 45825 | 2.2 | 2.2 | 100.00%
11.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 22-Jun-26 | 45828 | 8 | 8 | 100.00%
11.3 | 7TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 04-Apr-26 / 04-Apr-26 | 09-Apr-26 / 09-Apr-26 | - | 100 | 0 | 0.00%
11.3.1 | 110MM PVC CLEANOU T PLUG |  | 6 days | 04-Apr-26 / | 09-Apr-26 / 09-Apr-26 | - | 4 | 4 | 100.00%
11.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 09-Apr-26 | 45754 | 12.8 | 12.8 | 100.00%
11.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 09-Apr-26 | 45754 | 51.7 | 51.7 | 100.00%
11.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 09-Apr-26 | 45754 | 9 | 9 | 100.00%
11.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 09-Apr-26 | 45754 | 5 | 5 | 100.00%
11.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 09-Apr-26 | 45754 | 5 | 5 | 100.00%
11.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 09-Apr-26 | 45754 | 17 | 17 | 100.00%
11.4 | 7TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 09-May-26 / 09-May-26 | 13-May-26 / 13-May-26 | - | 100 | 0 | 0.00%
11.4.1 | 110MM PVC CLEANOU T PLUG |  | 5 days | 09-May-26 / | 13-May-26 / 13-May-26 | - | 4 | 4 | 100.00%
11.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 13-May-26 | 45788 | 12.8 | 12.8 | 100.00%
11.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 13-May-26 | 45788 | 51.7 | 51.7 | 100.00%
11.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 13-May-26 | 45788 | 9 | 9 | 100.00%
11.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 13-May-26 | 45788 | 5 | 5 | 100.00%
11.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 13-May-26 | 45788 | 5 | 5 | 100.00%
11.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 13-May-26 | 45788 | 17 | 17 | 100.00%
11.5 | 7TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 19-Sep-26 / | 21-Sep-26 / | - | 100 | 0 | 0.00%
11.5.1 | WATER CLOSET |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.3 | HEALTH FAUCET |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.4 | TWO WAY BIB COCK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.5 | TWIN ROBE HOOK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.6 | TOILET PAPER HOLDER |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.5.7 | WASH BASIN |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.5.9 | ANGLE VALVE |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.5.11 | URINAL BASIN |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.5.13 | SOAP DISPENS ER |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.6 | 7TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 19-Sep-26 / | 21-Sep-26 / | - | 100 | 0 | 0.00%
11.6.1 | WATER CLOSET |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.3 | HEALTH FAUCET |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.4 | TWO WAY BIB COCK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.5 | TWIN ROBE HOOK |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.6 | TOILET PAPER HOLDER |  | 1 days | 19-Sep-26 / | 19-Sep-26 / | - | 0 | 0 | 0.00%
11.6.7 | WASH BASIN |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.6.9 | ANGLE VALVE |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 0 | 0 | 0.00%
11.6.11 | URINAL BASIN |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.6.13 | SOAP DISPENS ER |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 21-Sep-26 / | 21-Sep-26 / | - | 0 | 0 | 0.00%
11.7 | 7TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
11.8 | 7TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
12 | 8TH FLOOR |  | 198 days | 11-Mar-26 / | 24-Sep-26 / | - | 0 | 0 | 0.00%
12.1 | 8TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 08-Jun-26 / 13-Jul-26 | 12-Jun-26 / 17-Jul-26 | - | 100 | 91.288 | 91.29%
12.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 08-Jun-26 / | 12-Jun-26 / 12-Jun-26 | - | 12.7 | 12.7 | 100.00%
12.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 08-Jun-26 / | 12-Jun-26 / 12-Jun-26 | - | 93.28 | 93.28 | 100.00%
12.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 12-Jun-26 | 45818 | 2.2 | 2.2 | 100.00%
12.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 12-Jun-26 | 45818 | 8 | 8 | 100.00%
12.2 | 8TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / 26-Jun-26 | / 03-Jul-26 | - | 100 | 30.263 | 30.26%
12.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 18-Jul-26 | 45854 | 10.85 | 10.85 | 100.00%
12.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 18-Jul-26 | 45854 | 94.53 | 94.53 | 100.00%
12.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 18-Jul-26 | 45854 | 2.2 | 2.2 | 100.00%
12.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 18-Jul-26 | 45854 | 8 | 8 | 100.00%
12.3 | 8TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 08-Jun-26 / 08-Jun-26 | 13-Jun-26 / 12-Jun-26 | - | 100 | 89.14 | 89.14%
12.3.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | / | / 13-Jun-26 | 45819 | 4 | 4 | 100.00%
12.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 6 days | 08-Jun-26 / | 13-Jun-26 / 13-Jun-26 | - | 12.8 | 12.8 | 100.00%
12.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 6 days | 08-Jun-26 / | 13-Jun-26 / 13-Jun-26 | - | 51.7 | 51.7 | 100.00%
12.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 13-Jun-26 | 45819 | 9 | 9 | 100.00%
12.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 13-Jun-26 | 45819 | 5 | 5 | 100.00%
12.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 13-Jun-26 | 45819 | 5 | 5 | 100.00%
12.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 13-Jun-26 | 45819 | 17 | 17 | 100.00%
12.4 | 8TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 68 days | 11-Mar-26 / 12-May-26 | 17-May-26 / 18-May-26 | - | 100 | 95.741 | 95.74%
12.4.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | / | / 17-May-26 | 45792 | 4 | 4 | 100.00%
12.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 7 days | 11-Mar-26 / | 17-Mar-26 / 17-May-26 | 61 | 14.55 | 14.55 | 100.00%
12.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 7 days | 11-May-26 / | 17-May-26 / 17-May-26 | - | 51.98 | 51.98 | 100.00%
12.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 17-May-26 | 45792 | 9 | 9 | 100.00%
12.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 17-May-26 | 45792 | 5 | 5 | 100.00%
12.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 17-May-26 | 45792 | 5 | 5 | 100.00%
12.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 17-May-26 | 45792 | 17 | 17 | 100.00%
12.5 | 8TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 22-Sep-26 / | 24-Sep-26 / | - | 100 | 0 | 0.00%
12.5.1 | WATER CLOSET |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.3 | HEALTH FAUCET |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.4 | TWO WAY BIB COCK |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.5 | TWIN ROBE HOOK |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.6 | TOILET PAPER HOLDER |  | 1 days | 22-Sep-26 / | 22-Sep-26 / | - | 0 | 0 | 0.00%
12.5.7 | WASH BASIN |  | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 0 | 0 | 0.00%
12.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 0 | 0 | 0.00%
12.5.9 | ANGLE VALVE |  | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 0 | 0 | 0.00%
12.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 0 | 0 | 0.00%
12.5.11 | URINAL BASIN |  | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 0 | 0 | 0.00%
12.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 0 | 0 | 0.00%
12.5.13 | SOAP DISPENS ER |  | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 0 | 0 | 0.00%
12.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 0 | 0 | 0.00%
12.6 | 8TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | - | 100 | 0 | 0.00%
12.6.1 | WATER CLOSET |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.3 | HEALTH FAUCET |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.4 | TWO WAY BIB COCK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.5 | TWIN ROBE HOOK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.6 | TOILET PAPER HOLDER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.7 | WASH BASIN |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.9 | ANGLE VALVE |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.11 | URINAL BASIN |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.13 | SOAP DISPENS ER |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.6.14 | SS SINGLE PIECE GRATING |  | 1 days | / | / | 45874 | 0 | 0 | 0.00%
12.7 | 8TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
12.8 | 8TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
13 | 9TH FLOOR |  | 115 days | 05-Jun-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.1 | 9TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 35 days | 20-Jun-26 / | 24-Jul-26 / | - | 100 | 77.071 | 77.07%
13.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 20-Jun-26 / | 26-Jun-26 / 25-Jul-26 | 29 | 10.85 | 10.85 | 100.00%
13.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 29-Jul-26 | 45865 | 94.53 | 94.53 | 100.00%
13.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 29-Jul-26 | 45865 | 2.2 | 2.2 | 100.00%
13.1.4 | 25 Mm Ball Valve |  | 1 days | / | / 29-Jul-26 | 45865 | 8 | 8 | 100.00%
13.1.5 | FASTNER ROD AND HANGER S FIXING |  | 1 days | 20-Jul-26 / 25-Jul-26 | 20-Jul-26 / 25-Jul-26 | 5 | 100 | 100 | 100.00%
13.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS, PRADIP BHIRAGI | 1 days | 20-Jul-26 / 21-Jul-26 | 20-Jul-26 / 26-Jul-26 | 6 | 100 | 100 | 100.00%
13.1.7 | WATER SUPPLY CHASING | APURBA BISWAS, PRADIP BHIRAGI | 1 days | 21-Jul-26 / 21-Jul-26 | 21-Jul-26 / 26-Jul-26 | 5 | 100 | 100 | 100.00%
13.1.8 | WATERSU PPLY HANGING LINE |  | 2 days | 22-Jul-26 / 27-Jul-26 | 23-Jul-26 / 29-Jul-26 | 6 | 100 | 100 | 100.00%
13.1.9 | WATER SUPPLY LINE, LEVEL & TESTING |  | 1 days | 23-Jul-26 / 30-Jul-26 | 23-Jul-26 / 31-Jul-26 | 8 | 100 | 0 | 0.00%
13.1.10 | WATERSU PPLY JARI REFILNG |  | 1 days | 24-Jul-26 / 31-Jul-26 | 24-Jul-26 / 31-Jul-26 | 7 | 100 | 0 | 0.00%
13.2 | 9TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 20-Jul-26 / | 24-Jul-26 / | - | 100 | 33.859 | 33.86%
13.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / 19-Jul-26 | / 22-Jul-26 | 45858 | 10.85 | 10.85 | 100.00%
13.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 22-Jul-26 | 45858 | 94.53 | 94.53 | 100.00%
13.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 1 days | / | / 22-Jul-26 | 45858 | 2.2 | 2.2 | 100.00%
13.2.4 | 25 Mm Ball Valve |  | 1 days | / | / 22-Jul-26 | 45858 | 8 | 8 | 100.00%
13.2.5 | WATER SUPPLY CHASING | APURBA BISWAS, PRADIP BHIRAGI | 1 days | 20-Jul-26 / 18-Jul-26 | 20-Jul-26 / 19-Jul-26 | - | 100 | 100 | 100.00%
13.2.6 | WATERSU PPLY HANGING LINE |  | 2 days | 21-Jul-26 / 19-Jul-26 | 22-Jul-26 / 22-Jul-26 | - | 100 | 0 | 0.00%
13.2.7 | WATER SUPPLY LINE, LEVEL & TESTING |  | 1 days | 23-Jul-26 / 23-Jul-26 | 23-Jul-26 / 23-Jul-26 | - | 100 | 0 | 0.00%
13.2.8 | WATERSU PPLY JARI REFILNG |  | 1 days | 24-Jul-26 / 24-Jul-26 | 24-Jul-26 / 24-Jul-26 | - | 100 | 0 | 0.00%
13.3 | 9TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 05-Jun-26 / | 10-Jun-26 / | - | 100 | 15.454 | 15.45%
13.3.1 | 110MM PVC CLEANOU T PLUG |  | 6 days | 05-Jun-26 / | 10-Jun-26 / 15-Jun-26 | 5 | 4 | 4 | 100.00%
13.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 15-Jun-26 | 45821 | 14.98 | 12.8 | 85.45%
13.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 15-Jun-26 | 45821 | 43.36 | 43.36 | 100.00%
13.3.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 15-Jun-26 | 45821 | 9 | 9 | 100.00%
13.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 15-Jun-26 | 45821 | 5 | 5 | 100.00%
13.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 15-Jun-26 | 45821 | 5 | 5 | 100.00%
13.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 15-Jun-26 | 45821 | 17 | 17 | 100.00%
13.4 | 9TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 05-Jun-26 / | 10-Jun-26 / | - | 100 | 98.788 | 98.79%
13.4.1 | 110MM PVC CLEANOU T PLUG |  | 6 days | 05-Jun-26 / | 10-Jun-26 / 15-Jun-26 | 5 | 4 | 4 | 100.00%
13.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 15-Jun-26 | 45821 | 14.98 | 12.8 | 85.45%
13.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | / | / 15-Jun-26 | 45821 | 43.36 | 43.36 | 100.00%
13.4.4 | 110 X 110MM P- TRAP |  | 1 days | / | / 15-Jun-26 | 45821 | 9 | 9 | 100.00%
13.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | / | / 15-Jun-26 | 45821 | 5 | 5 | 100.00%
13.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | / | / 15-Jun-26 | 45821 | 5 | 5 | 100.00%
13.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | / | / 15-Jun-26 | 45821 | 17 | 17 | 100.00%
13.5 | 9TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 25-Sep-26 / | 27-Sep-26 / | - | 100 | 0 | 0.00%
13.5.1 | WATER CLOSET |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.3 | HEALTH FAUCET |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.4 | TWO WAY BIB COCK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.5 | TWIN ROBE HOOK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.6 | TOILET PAPER HOLDER |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.5.7 | WASH BASIN |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.5.9 | ANGLE VALVE |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.5.11 | URINAL BASIN |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.5.13 | SOAP DISPENS ER |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.6 | 9TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 25-Sep-26 / | 27-Sep-26 / | - | 100 | 0 | 0.00%
13.6.1 | WATER CLOSET |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.3 | HEALTH FAUCET |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.4 | TWO WAY BIB COCK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.5 | TWIN ROBE HOOK |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.6 | TOILET PAPER HOLDER |  | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 0 | 0 | 0.00%
13.6.7 | WASH BASIN |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.6.9 | ANGLE VALVE |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 0 | 0 | 0.00%
13.6.11 | URINAL BASIN |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.6.13 | SOAP DISPENS ER |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 0 | 0 | 0.00%
13.7 | 9TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
13.8 | 9TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
14 | 10TH FLOOR |  | 110 days | 13-Jun-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.1 | 10TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 29 days | 28-Jun-26 / | 26-Jul-26 / | - | 100 | 78.961 | 78.96%
14.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | PRADIP BHIRAGI | 7 days | 28-Jun-26 / 20-Jun-26 | 04-Jul-26 / 17-Jul-26 | 13 | 29.57 | 29.57 | 100.00%
14.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 22-Jul-26 / | 26-Jul-26 / 17-Jul-26 | - | 89.2 | 89.2 | 100.00%
14.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 20-Jul-26 / | 26-Jul-26 / 17-Jul-26 | - | 2.2 | 2.2 | 100.00%
14.1.4 | 25 Mm Ball Valve |  | 7 days | 20-Jul-26 / | 26-Jul-26 / 17-Jul-26 | - | 8 | 8 | 100.00%
14.2 | 10TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 29 days | 28-Jun-26 / | 26-Jul-26 / | - | 100 | 100 | 100.00%
14.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | PRADIP BHIRAGI | 7 days | 28-Jun-26 / | 04-Jul-26 / 17-Jul-26 | 13 | 29.57 | 29.57 | 100.00%
14.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 5 days | 22-Jul-26 / | 26-Jul-26 / 17-Jul-26 | - | 89.2 | 89.2 | 100.00%
14.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 7 days | 28-Jun-26 / | 04-Jul-26 / 17-Jul-26 | 13 | 2.2 | 2.2 | 100.00%
14.2.4 | 25 Mm Ball Valve |  | 7 days | 20-Jul-26 / | 26-Jul-26 / 17-Jul-26 | - | 8 | 8 | 100.00%
14.3 | 10TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 18 days | 13-Jun-26 / | 30-Jun-26 / | - | 100 | 68.182 | 68.18%
14.3.1 | 110MM PVC CLEANOU T PLUG |  | 6 days | 13-Jun-26 / 20-Jun-26 | 18-Jun-26 / 10-Jul-26 | 22 | 4 | 4 | 100.00%
14.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 11 days | 20-Jun-26 / 20-Jun-26 | 30-Jun-26 / 10-Jul-26 | 10 | 12.8 | 12.8 | 100.00%
14.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 10-Jul-26 | 20 | 43.36 | 43.36 | 100.00%
14.3.4 | 110 X 110MM P- TRAP |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 10-Jul-26 | 20 | 9 | 9 | 100.00%
14.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 10-Jul-26 | 20 | 5 | 5 | 100.00%
14.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 31-May-26 | - | 5 | 5 | 100.00%
14.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 31-May-26 | - | 17 | 17 | 100.00%
14.4 | 10TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 20-Jun-26 / | 25-Jun-26 / | - | 100 | 83.333 | 83.33%
14.4.1 | 110MM PVC CLEANOU T PLUG |  | 6 days | 20-Jun-26 / | 25-Jun-26 / 07-Jul-26 | 12 | 4 | 4 | 100.00%
14.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 07-Jul-26 | 17 | 14.98 | 14.98 | 100.00%
14.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 07-Jul-26 | 17 | 43.36 | 43.36 | 100.00%
14.4.4 | 110 X 110MM P- TRAP |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 07-Jul-26 | 17 | 9 | 9 | 100.00%
14.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 07-Jul-26 | 17 | 5 | 5 | 100.00%
14.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 31-May-26 | - | 5 | 5 | 100.00%
14.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 20-Jun-26 / | 20-Jun-26 / 31-May-26 | - | 17 | 17 | 100.00%
14.5 | 10TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 28-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
14.5.1 | WATER CLOSET |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.3 | HEALTH FAUCET |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.4 | TWO WAY BIB COCK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.5 | TWIN ROBE HOOK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.6 | TOILET PAPER HOLDER |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.5.7 | WASH BASIN |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.5.9 | ANGLE VALVE |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.5.11 | URINAL BASIN |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.5.13 | SOAP DISPENS ER |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.6 | 10TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 28-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
14.6.1 | WATER CLOSET |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.3 | HEALTH FAUCET |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.4 | TWO WAY BIB COCK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.5 | TWIN ROBE HOOK |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.6 | TOILET PAPER HOLDER |  | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 0 | 0 | 0.00%
14.6.7 | WASH BASIN |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.6.9 | ANGLE VALVE |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 0 | 0 | 0.00%
14.6.11 | URINAL BASIN |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.6.13 | SOAP DISPENS ER |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
14.7 | 10TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
14.8 | 10TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
15 | 11TH FLOOR |  | 106 days | 20-Jun-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.1 | 11TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 9 days | 08-Jul-26 / | 16-Jul-26 / | - | 100 | 92.683 | 92.68%
15.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | SUKANTA, GOURAB | 9 days | 08-Jul-26 / 27-Jun-26 | 16-Jul-26 / 13-Jul-26 | - | 12.7 | 12.7 | 100.00%
15.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 8 days | 08-Jul-26 / 08-Jul-26 | 15-Jul-26 / 13-Jul-26 | - | 93.28 | 93.28 | 100.00%
15.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 8 days | 08-Jul-26 / 08-Jul-26 | 15-Jul-26 / 13-Jul-26 | - | 2.2 | 2.2 | 100.00%
15.1.4 | 25 Mm Ball Valve |  | 8 days | 08-Jul-26 / 08-Jul-26 | 15-Jul-26 / 13-Jul-26 | - | 8 | 8 | 100.00%
15.1.5 | FASTNER ROD AND HANGER S FIXING |  | 1 days | 08-Jul-26 / 08-Jul-26 | 08-Jul-26 / 08-Jul-26 | - | 100 | 100 | 100.00%
15.1.6 | WATER SUPPLY JARI MARKING |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 09-Jul-26 | - | 100 | 100 | 100.00%
15.1.7 | WATER SUPPLY CHASING |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 09-Jul-26 | - | 100 | 100 | 100.00%
15.1.8 | WATERSU PPLY HANGING LINE |  | 2 days | 10-Jul-26 / | 11-Jul-26 / 10-Jul-26 | - | 100 | 100 | 100.00%
15.1.9 | WATERSU PPLY CONCEAL LINE |  | 1 days | 08-Jul-26 / | 08-Jul-26 / | 30 | 100 | 0 | 0.00%
15.1.10 | WATERSU PPLY JARI REFILNG |  | 1 days | 08-Jul-26 / | 08-Jul-26 / | 30 | 100 | 0 | 0.00%
15.1.11 | WATER SUPPLY LINE, LEVEL & TESTING |  | 1 days | 08-Jul-26 / | 08-Jul-26 / | 30 | 100 | 0 | 0.00%
15.2 | 11TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 4 days | 08-Jul-26 / | 11-Jul-26 / | - | 100 | 50 | 50.00%
15.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 10-Jul-26 / 25-Jul-26 | 11-Jul-26 / 01-Aug-26 | 21 | 12.7 | 12.7 | 100.00%
15.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 10-Jul-26 / 10-Jul-26 | 11-Jul-26 / 11-Jul-26 | - | 93.28 | 93.28 | 100.00%
15.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 10-Jul-26 / 10-Jul-26 | 11-Jul-26 / 11-Jul-26 | - | 2.2 | 2.2 | 100.00%
15.2.4 | 25 Mm Ball Valve |  | 2 days | 10-Jul-26 / 10-Jul-26 | 11-Jul-26 / 11-Jul-26 | - | 8 | 8 | 100.00%
15.2.5 | FASTNER ROD AND HANGER S FIXING |  | 1 days | 08-Jul-26 / 08-Jul-26 | 08-Jul-26 / 08-Jul-26 | - | 100 | 0 | 0.00%
15.2.6 | WATER SUPPLY JARI MARKING |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 09-Jul-26 | - | 100 | 0 | 0.00%
15.2.7 | WATER SUPPLY CHASING |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 09-Jul-26 | - | 100 | 0 | 0.00%
15.2.8 | WATERSU PPLY HANGING LINE |  | 2 days | 10-Jul-26 / 10-Jul-26 | 11-Jul-26 / 11-Jul-26 | - | 100 | 0 | 0.00%
15.2.9 | WATERSU PPLY CONCEAL LINE |  | 1 days | 09-Jul-26 / | 09-Jul-26 / | 29 | 100 | 0 | 0.00%
15.2.10 | WATERSU PPLY JARI REFILNG |  | 1 days | 09-Jul-26 / | 09-Jul-26 / | 29 | 100 | 0 | 0.00%
15.2.11 | WATER SUPPLY LINE, LEVEL & TESTING |  | 1 days | 09-Jul-26 / | 09-Jul-26 / | 29 | 100 | 0 | 0.00%
15.3 | 11TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 10 days | 08-Jul-26 / | 17-Jul-26 / | - | 100 | 73.077 | 73.08%
15.3.1 | 110MM PVC CLEANOU T PLUG |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 10-Jul-26 | 1 | 4 | 4 | 100.00%
15.3.2 | 50MM PVC SWR TYPE-B SELFIT |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 14.28 | 14.28 | 100.00%
15.3.3 | 110MM PVC SWR TYPE-B SELFIT |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 51.98 | 51.98 | 100.00%
15.3.4 | 110 X 110MM P- TRAP |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 9 | 9 | 100.00%
15.3.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 5 | 5 | 100.00%
15.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 08-Jul-26 / 08-Jul-26 | 08-Jul-26 / 08-Jul-26 | - | 5 | 5 | 100.00%
15.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 08-Jul-26 / 08-Jul-26 | 08-Jul-26 / 08-Jul-26 | - | 17 | 17 | 100.00%
15.3.8 | SOIL LINE HANGING |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 100 | 100 | 100.00%
15.3.9 | WASTE LINE HANGING |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 100 | 100 | 100.00%
15.3.10 | DRAINAG E JARI MARKING |  | 2 days | 11-Jul-26 / 11-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 100 | 100 | 100.00%
15.3.11 | DRAINAG E CHASING |  | 2 days | 11-Jul-26 / 11-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 100 | 100 | 100.00%
15.3.12 | WASHBA SIN OUTLET CONNEC TION |  | 1 days | 12-Jul-26 / 12-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 100 | 100 | 100.00%
15.3.13 | URINAL OUTLET CONNEC TION |  | 1 days | 13-Jul-26 / 13-Jul-26 | 13-Jul-26 / 13-Jul-26 | - | 100 | 100 | 100.00%
15.3.14 | WC OUTLET CONNEC TION |  | 1 days | 14-Jul-26 / 14-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 100 | 0 | 0.00%
15.3.15 | FLUSH TANK FIXING |  | 1 days | 15-Jul-26 / 15-Jul-26 | 15-Jul-26 / 15-Jul-26 | - | 100 | 0 | 0.00%
15.3.16 | URINAL SENSOR FIXING |  | 1 days | 16-Jul-26 / 16-Jul-26 | 16-Jul-26 / 16-Jul-26 | - | 100 | 0 | 0.00%
15.3.17 | DRAINAG E JARI REFILLIN G |  | 1 days | 17-Jul-26 / 17-Jul-26 | 17-Jul-26 / 17-Jul-26 | - | 100 | 0 | 0.00%
15.3.18 | DRAINAG E LINE, LEVEL & TESTING |  | 1 days | 17-Jul-26 / | 17-Jul-26 / | 21 | 100 | 0 | 0.00%
15.4 | 11TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 51 days | 20-Jun-26 / | 09-Aug-26 / | - | 100 | 49.105 | 49.10%
15.4.1 | 110MM PVC CLEANOU T PLUG |  | 4 days | 20-Jun-26 / 09-Jul-26 | 23-Jun-26 / 09-Jul-26 | 16 | 4 | 4 | 100.00%
15.4.2 | 50MM PVC SWR TYPE-B SELFIT |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 10-Jul-26 | 1 | 14.28 | 14.28 | 100.00%
15.4.3 | 110MM PVC SWR TYPE-B SELFIT |  | 2 days | 09-Jul-26 / 09-Jul-26 | 10-Jul-26 / 10-Jul-26 | - | 51.98 | 51.98 | 100.00%
15.4.4 | 110 X 110MM P- TRAP |  | 1 days | 09-Jul-26 / 09-Jul-26 | 09-Jul-26 / 10-Jul-26 | 1 | 9 | 9 | 100.00%
15.4.5 | SELFIT SWR TYPE-B HIGHRISE R |  | 1 days | 09-Aug-26 / 09-Jul-26 | 09-Aug-26 / 10-Jul-26 | - | 5 | 5 | 100.00%
15.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 2 days | 08-Aug-26 / 08-Jul-26 | 09-Aug-26 / 08-Jul-26 | - | 5 | 5 | 100.00%
15.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 08-Jul-26 / 08-Jul-26 | 08-Jul-26 / 08-Jul-26 | - | 17 | 5 | 29.41%
15.4.8 | SOIL LINE HANGING |  | 1 days | 13-Jul-26 / 09-Jul-26 | 13-Jul-26 / 10-Jul-26 | - | 100 | 0 | 0.00%
15.4.9 | WASTE LINE HANGING |  | 1 days | 16-Jul-26 / 09-Jul-26 | 16-Jul-26 / 10-Jul-26 | - | 100 | 0 | 0.00%
15.4.10 | DRAINAG E JARI MARKING |  | 1 days | 16-Jul-26 / 11-Jul-26 | 16-Jul-26 / 12-Jul-26 | - | 100 | 0 | 0.00%
15.4.11 | DRAINAG E CHASING |  | 1 days | 16-Jul-26 / 11-Jul-26 | 16-Jul-26 / 12-Jul-26 | - | 100 | 0 | 0.00%
15.4.12 | WASHBA SIN OUTLET CONNEC TION |  | 1 days | 16-Jul-26 / 12-Jul-26 | 16-Jul-26 / 12-Jul-26 | - | 100 | 0 | 0.00%
15.4.13 | URINAL OUTLET CONNEC TION |  | 1 days | 16-Jul-26 / 13-Jul-26 | 16-Jul-26 / 13-Jul-26 | - | 100 | 0 | 0.00%
15.4.14 | WC OUTLET CONNEC TION |  | 1 days | 16-Jul-26 / 14-Jul-26 | 16-Jul-26 / 14-Jul-26 | - | 100 | 0 | 0.00%
15.4.15 | FLUSH TANK FIXING |  | 1 days | 15-Jul-26 / 15-Jul-26 | 15-Jul-26 / 15-Jul-26 | - | 100 | 0 | 0.00%
15.4.16 | URINAL SENSOR FIXING |  | 1 days | 15-Jul-26 / 16-Jul-26 | 15-Jul-26 / 16-Jul-26 | 1 | 100 | 0 | 0.00%
15.4.17 | DRAINAG E JARI REFILLIN G |  | 1 days | 15-Jul-26 / 17-Jul-26 | 15-Jul-26 / 17-Jul-26 | 2 | 100 | 0 | 0.00%
15.4.18 | DRAINAG E LINE, LEVEL & TESTING |  | 1 days | 15-Jul-26 / | 15-Jul-26 / | 23 | 100 | 0 | 0.00%
15.5 | 11TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 01-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
15.5.1 | WATER CLOSET |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.3 | HEALTH FAUCET |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.4 | TWO WAY BIB COCK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.5 | TWIN ROBE HOOK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.6 | TOILET PAPER HOLDER |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.5.7 | WASH BASIN |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.5.9 | ANGLE VALVE |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.5.11 | URINAL BASIN |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.5.13 | SOAP DISPENS ER |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.6 | 11TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 01-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
15.6.1 | WATER CLOSET |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.3 | HEALTH FAUCET |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.4 | TWO WAY BIB COCK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.5 | TWIN ROBE HOOK |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.6 | TOILET PAPER HOLDER |  | 1 days | 01-Oct-26 / | 01-Oct-26 / | - | 0 | 0 | 0.00%
15.6.7 | WASH BASIN |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.6.9 | ANGLE VALVE |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 0 | 0 | 0.00%
15.6.11 | URINAL BASIN |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.6.13 | SOAP DISPENS ER |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 0 | 0 | 0.00%
15.7 | 11TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
15.8 | 11TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
16 | 12TH FLOOR |  | 87 days | 12-Jul-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.1 | 12TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 06-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
16.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 26.2 | 0 | 0.00%
16.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 94 | 0 | 0.00%
16.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 6 | 0 | 0.00%
16.1.4 | 25 Mm Ball Valve |  | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 8 | 0 | 0.00%
16.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
16.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 2 days | 06-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
16.1.7 | WATER SUPPLY CHASING | MANOJ | 2 days | 06-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
16.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.1.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
16.2 | 12TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 06-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
16.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | SUKANTA, GOURAB | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 26.2 | 0 | 0.00%
16.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | SUKANTA, GOURAB | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 94 | 0 | 0.00%
16.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | SUKANTA, GOURAB | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 6 | 0 | 0.00%
16.2.4 | 25 Mm Ball Valve | SUKANTA, GOURAB | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 8 | 0 | 0.00%
16.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
16.2.6 | WATER SUPPLY JARI MARKING | MANOJ | 2 days | 06-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
16.2.7 | WATER SUPPLY CHASING | MANOJ | 2 days | 06-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
16.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 2 days | 08-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.2.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
16.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
16.3 | 12TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 12-Jul-26 / | 22-Jul-26 / | - | 100 | 0 | 0.00%
16.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 2 days | 13-Jul-26 / 13-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 4 | 0 | 0.00%
16.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 2 days | 13-Jul-26 / 13-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 14.28 | 0 | 0.00%
16.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 2 days | 13-Jul-26 / 13-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 51.98 | 0 | 0.00%
16.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 2 days | 13-Jul-26 / 13-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 9 | 0 | 0.00%
16.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 2 days | 13-Jul-26 / 13-Jul-26 | 14-Jul-26 / 14-Jul-26 | - | 5 | 0 | 0.00%
16.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 12-Jul-26 / 12-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 5 | 0 | 0.00%
16.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 12-Jul-26 / 12-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 17 | 0 | 0.00%
16.3.8 | DRAINAG E JARI MARKING | MANOJ | 1 days | 15-Jul-26 / 15-Jul-26 | 15-Jul-26 / 15-Jul-26 | - | 100 | 0 | 0.00%
16.3.9 | DRAINAG E CHASING | MANOJ | 1 days | 15-Jul-26 / 15-Jul-26 | 15-Jul-26 / 15-Jul-26 | - | 100 | 0 | 0.00%
16.3.10 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 16-Jul-26 / 16-Jul-26 | 16-Jul-26 / 16-Jul-26 | - | 100 | 0 | 0.00%
16.3.11 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 17-Jul-26 / 17-Jul-26 | 17-Jul-26 / 17-Jul-26 | - | 100 | 0 | 0.00%
16.3.12 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 18-Jul-26 / 18-Jul-26 | 18-Jul-26 / 18-Jul-26 | - | 100 | 0 | 0.00%
16.3.13 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 19-Jul-26 / 19-Jul-26 | 19-Jul-26 / 19-Jul-26 | - | 100 | 0 | 0.00%
16.3.14 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 20-Jul-26 / 20-Jul-26 | 20-Jul-26 / 20-Jul-26 | - | 100 | 0 | 0.00%
16.3.15 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 21-Jul-26 / 21-Jul-26 | 21-Jul-26 / 21-Jul-26 | - | 100 | 0 | 0.00%
16.3.16 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 22-Jul-26 / | 22-Jul-26 / | 16 | 100 | 0 | 0.00%
16.4 | 12TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 12-Jul-26 / | 22-Jul-26 / | - | 100 | 15.625 | 15.63%
16.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 13-Jul-26 / | 15-Jul-26 / | 23 | 4 | 0 | 0.00%
16.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 13-Jul-26 / | 15-Jul-26 / | 23 | 14.28 | 0 | 0.00%
16.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 13-Jul-26 / | 15-Jul-26 / | 23 | 51.98 | 0 | 0.00%
16.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 13-Jul-26 / | 15-Jul-26 / | 23 | 9 | 0 | 0.00%
16.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 13-Jul-26 / | 15-Jul-26 / | 23 | 5 | 0 | 0.00%
16.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 12-Jul-26 / 12-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 5 | 5 | 100.00%
16.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 12-Jul-26 / 12-Jul-26 | 12-Jul-26 / 12-Jul-26 | - | 17 | 17 | 100.00%
16.4.8 | SOIL LINE HANGING | SUKANTA, GOURAB | 3 days | 13-Jul-26 / 20-Jul-26 | 15-Jul-26 / | 23 | 100 | 100 | 100.00%
16.4.9 | WASTE LINE HANGING | SUKANTA, GOURAB | 3 days | 13-Jul-26 / 20-Jul-26 | 15-Jul-26 / | 23 | 100 | 0 | 0.00%
16.4.10 | DRAINAG E JARI MARKING | SUKANTA, MANOJ | 1 days | 15-Jul-26 / | 15-Jul-26 / | 23 | 100 | 0 | 0.00%
16.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 15-Jul-26 / | 15-Jul-26 / | 23 | 100 | 0 | 0.00%
16.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 16-Jul-26 / | 16-Jul-26 / | 22 | 100 | 0 | 0.00%
16.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 17-Jul-26 / | 17-Jul-26 / | 21 | 100 | 0 | 0.00%
16.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 18-Jul-26 / | 18-Jul-26 / | 20 | 100 | 0 | 0.00%
16.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 19-Jul-26 / | 19-Jul-26 / | 19 | 100 | 0 | 0.00%
16.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 20-Jul-26 / | 20-Jul-26 / | 18 | 100 | 0 | 0.00%
16.4.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 21-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
16.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 22-Jul-26 / | 22-Jul-26 / | 16 | 100 | 0 | 0.00%
16.5 | 12TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 04-Oct-26 / | 06-Oct-26 / | - | 100 | 0 | 0.00%
16.5.1 | WATER CLOSET |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.3 | HEALTH FAUCET |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.4 | TWO WAY BIB COCK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.5 | TWIN ROBE HOOK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.6 | TOILET PAPER HOLDER |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.5.7 | WASH BASIN |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.5.9 | ANGLE VALVE |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.5.11 | URINAL BASIN |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.5.13 | SOAP DISPENS ER |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.6 | 12TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 04-Oct-26 / | 06-Oct-26 / | - | 100 | 0 | 0.00%
16.6.1 | WATER CLOSET |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.3 | HEALTH FAUCET |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.4 | TWO WAY BIB COCK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.5 | TWIN ROBE HOOK |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.6 | TOILET PAPER HOLDER |  | 1 days | 04-Oct-26 / | 04-Oct-26 / | - | 0 | 0 | 0.00%
16.6.7 | WASH BASIN |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.6.9 | ANGLE VALVE |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 05-Oct-26 / | 05-Oct-26 / | - | 0 | 0 | 0.00%
16.6.11 | URINAL BASIN |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.6.13 | SOAP DISPENS ER |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Oct-26 / | 06-Oct-26 / | - | 0 | 0 | 0.00%
16.7 | 12TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
16.8 | 12TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
17 | 13TH FLOOR |  | 84 days | 18-Jul-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.1 | 13TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 12-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
17.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 12.7 | 0 | 0.00%
17.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 94 | 0 | 0.00%
17.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 6 | 0 | 0.00%
17.1.4 | 25 Mm Ball Valve |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 8 | 0 | 0.00%
17.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
17.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
17.1.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
17.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
17.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
17.1.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
17.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
17.2 | 13TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 12-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
17.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 12.7 | 0 | 0.00%
17.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 94 | 0 | 0.00%
17.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 6 | 0 | 0.00%
17.2.4 | 25 Mm Ball Valve |  | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 8 | 0 | 0.00%
17.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
17.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
17.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
17.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
17.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 2 days | 14-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
17.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
17.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
17.3 | 13TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 18-Jul-26 / | 28-Jul-26 / | - | 100 | 3.125 | 3.13%
17.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 4 | 0 | 0.00%
17.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 14.28 | 0 | 0.00%
17.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 51.98 | 0 | 0.00%
17.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 9 | 0 | 0.00%
17.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 5 | 0 | 0.00%
17.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 18-Jul-26 / 18-Jul-26 | 18-Jul-26 / 18-Jul-26 | - | 5 | 0 | 0.00%
17.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM |  | 1 days | 18-Jul-26 / 18-Jul-26 | 18-Jul-26 / 18-Jul-26 | - | 17 | 0 | 0.00%
17.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.3.10 | DRAINAG E JARI MARKING | PRADIP BHIRAGI, MANOJ | 1 days | 21-Jul-26 / 22-Jul-26 | 21-Jul-26 / | 17 | 100 | 50 | 50.00%
17.3.11 | DRAINAG E CHASING | MANOJ | 1 days | 21-Jul-26 / 22-Jul-26 | 21-Jul-26 / | 17 | 100 | 50 | 50.00%
17.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 22-Jul-26 / | 22-Jul-26 / | 16 | 100 | 0 | 0.00%
17.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 23-Jul-26 / | 23-Jul-26 / | 15 | 100 | 0 | 0.00%
17.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 24-Jul-26 / | 24-Jul-26 / | 14 | 100 | 0 | 0.00%
17.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 25-Jul-26 / | 25-Jul-26 / | 13 | 100 | 0 | 0.00%
17.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 26-Jul-26 / | 26-Jul-26 / | 12 | 100 | 0 | 0.00%
17.3.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 27-Jul-26 / | 27-Jul-26 / | 11 | 100 | 0 | 0.00%
17.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 28-Jul-26 / | 28-Jul-26 / | 10 | 100 | 0 | 0.00%
17.4 | 13TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 18-Jul-26 / | 28-Jul-26 / | - | 100 | 0 | 0.00%
17.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 4 | 0 | 0.00%
17.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 14.28 | 0 | 0.00%
17.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 51.98 | 0 | 0.00%
17.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 9 | 0 | 0.00%
17.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 5 | 0 | 0.00%
17.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM |  | 1 days | 18-Jul-26 / | 18-Jul-26 / | 20 | 5 | 0 | 0.00%
17.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 18-Jul-26 / | 18-Jul-26 / | 20 | 17 | 0 | 0.00%
17.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 19-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.4.10 | DRAINAG E JARI MARKING | MANOJ | 1 days | 21-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 21-Jul-26 / | 21-Jul-26 / | 17 | 100 | 0 | 0.00%
17.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 22-Jul-26 / | 22-Jul-26 / | 16 | 100 | 0 | 0.00%
17.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 23-Jul-26 / | 23-Jul-26 / | 15 | 100 | 0 | 0.00%
17.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 24-Jul-26 / | 24-Jul-26 / | 14 | 100 | 0 | 0.00%
17.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 25-Jul-26 / | 25-Jul-26 / | 13 | 100 | 0 | 0.00%
17.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 26-Jul-26 / | 26-Jul-26 / | 12 | 100 | 0 | 0.00%
17.4.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 27-Jul-26 / | 27-Jul-26 / | 11 | 100 | 0 | 0.00%
17.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 28-Jul-26 / | 28-Jul-26 / | 10 | 100 | 0 | 0.00%
17.5 | 13TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 07-Oct-26 / | 09-Oct-26 / | - | 100 | 0 | 0.00%
17.5.1 | WATER CLOSET |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.3 | HEALTH FAUCET |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.4 | TWO WAY BIB COCK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.5 | TWIN ROBE HOOK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.6 | TOILET PAPER HOLDER |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.5.7 | WASH BASIN |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.5.9 | ANGLE VALVE |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.5.11 | URINAL BASIN |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.5.13 | SOAP DISPENS ER |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.6 | 13TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 07-Oct-26 / | 09-Oct-26 / | - | 100 | 0 | 0.00%
17.6.1 | WATER CLOSET |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.3 | HEALTH FAUCET |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.4 | TWO WAY BIB COCK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.5 | TWIN ROBE HOOK |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.6 | TOILET PAPER HOLDER |  | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 0 | 0 | 0.00%
17.6.7 | WASH BASIN |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.6.9 | ANGLE VALVE |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 08-Oct-26 / | 08-Oct-26 / | - | 0 | 0 | 0.00%
17.6.11 | URINAL BASIN |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.6.13 | SOAP DISPENS ER |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Oct-26 / | 09-Oct-26 / | - | 0 | 0 | 0.00%
17.7 | 13TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
17.8 | 13TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
18 | 14TH FLOOR |  |  | / | / | - | 0 | 0 | 0.00%
18.1 | TERRACE LOOPING |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
19 | 15TH FLOOR |  | 70 days | 07-Aug-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.1 | 15TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 01-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 12.7 | 0 | 0.00%
19.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 94 | 0 | 0.00%
19.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 2.2 | 0 | 0.00%
19.1.4 | 25 Mm Ball Valve |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 8 | 0 | 0.00%
19.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 100 | 0 | 0.00%
19.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 100 | 0 | 0.00%
19.1.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
19.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 100 | 0 | 0.00%
19.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.1.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 100 | 0 | 0.00%
19.2 | 15TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 01-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 12.7 | 0 | 0.00%
19.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 94 | 0 | 0.00%
19.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 2.2 | 0 | 0.00%
19.2.4 | 25 Mm Ball Valve |  | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 8 | 0 | 0.00%
19.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 100 | 0 | 0.00%
19.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 01-Sep-26 / | 01-Sep-26 / | - | 100 | 0 | 0.00%
19.2.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
19.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 03-Sep-26 / | 04-Sep-26 / | - | 100 | 0 | 0.00%
19.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.2.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
19.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 04-Sep-26 / | 04-Sep-26 / | - | 100 | 0 | 0.00%
19.3 | 15TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 07-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
19.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 4 | 0 | 0.00%
19.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 14.28 | 0 | 0.00%
19.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 51.98 | 0 | 0.00%
19.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 9 | 0 | 0.00%
19.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 5 | 0 | 0.00%
19.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 5 | 0 | 0.00%
19.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 17 | 0 | 0.00%
19.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
19.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
19.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
19.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
19.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 14-Aug-26 / | 14-Aug-26 / | - | 100 | 0 | 0.00%
19.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 15-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
19.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
19.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
19.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
19.4 | 15TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 07-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
19.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 4 | 0 | 0.00%
19.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 14.28 | 0 | 0.00%
19.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 51.98 | 0 | 0.00%
19.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 9 | 0 | 0.00%
19.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 5 | 0 | 0.00%
19.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 5 | 0 | 0.00%
19.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 17 | 0 | 0.00%
19.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 08-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.4.10 | DRAINAG E JARI MARKING | MANOJ | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
19.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
19.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
19.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
19.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 14-Aug-26 / | 14-Aug-26 / | - | 100 | 0 | 0.00%
19.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 15-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
19.4.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
19.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
19.5 | 15TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 13-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
19.5.1 | WATER CLOSET |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.3 | HEALTH FAUCET |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.4 | TWO WAY BIB COCK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.5 | TWIN ROBE HOOK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.6 | TOILET PAPER HOLDER |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.5.7 | WASH BASIN |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.5.9 | ANGLE VALVE |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.5.11 | URINAL BASIN |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.5.13 | SOAP DISPENS ER |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.6 | 15TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 13-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
19.6.1 | WATER CLOSET |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.3 | HEALTH FAUCET |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.4 | TWO WAY BIB COCK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.5 | TWIN ROBE HOOK |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.6 | TOILET PAPER HOLDER |  | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 0 | 0 | 0.00%
19.6.7 | WASH BASIN |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.6.9 | ANGLE VALVE |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 0 | 0 | 0.00%
19.6.11 | URINAL BASIN |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.6.13 | SOAP DISPENS ER |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
19.7 | 15TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
19.8 | 15TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
20 | 16TH FLOOR |  | 82 days | 29-Jul-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.1 | 16TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 23-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 12.7 | 0 | 0.00%
20.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 94 | 0 | 0.00%
20.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 2.2 | 0 | 0.00%
20.1.4 | 25 Mm Ball Valve |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 8 | 0 | 0.00%
20.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
20.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
20.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 24-Aug-26 / | 24-Aug-26 / | - | 100 | 0 | 0.00%
20.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
20.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
20.2 | 16TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 23-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 12.7 | 0 | 0.00%
20.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 94 | 0 | 0.00%
20.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 2.2 | 0 | 0.00%
20.2.4 | 25 Mm Ball Valve |  | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 8 | 0 | 0.00%
20.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
20.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
20.2.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 24-Aug-26 / | 24-Aug-26 / | - | 100 | 0 | 0.00%
20.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 25-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
20.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.2.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
20.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
20.3 | 16TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 29-Jul-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
20.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 4 | 0 | 0.00%
20.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 14.28 | 0 | 0.00%
20.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 51.98 | 0 | 0.00%
20.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 9 | 0 | 0.00%
20.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 5 | 0 | 0.00%
20.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 29-Jul-26 / | 29-Jul-26 / | 9 | 5 | 0 | 0.00%
20.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 29-Jul-26 / | 29-Jul-26 / | 9 | 17 | 0 | 0.00%
20.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.3.10 | DRAINAG E JARI MARKING | MANOJ | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.3.11 | DRAINAG E CHASING | MANOJ | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 02-Aug-26 / | 02-Aug-26 / | 5 | 100 | 0 | 0.00%
20.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
20.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
20.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
20.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
20.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
20.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
20.4 | 16TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 29-Jul-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
20.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 4 | 0 | 0.00%
20.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 14.28 | 0 | 0.00%
20.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 51.98 | 0 | 0.00%
20.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 9 | 0 | 0.00%
20.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 5 | 0 | 0.00%
20.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 29-Jul-26 / | 29-Jul-26 / | 9 | 5 | 0 | 0.00%
20.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 29-Jul-26 / | 29-Jul-26 / | 9 | 17 | 0 | 0.00%
20.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 30-Jul-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.4.10 | DRAINAG E JARI MARKING | MANOJ | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 100 | 0 | 0.00%
20.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 02-Aug-26 / | 02-Aug-26 / | 5 | 100 | 0 | 0.00%
20.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
20.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
20.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
20.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
20.4.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
20.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
20.5 | 16TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 16-Oct-26 / | 18-Oct-26 / | - | 100 | 0 | 0.00%
20.5.1 | WATER CLOSET |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.3 | HEALTH FAUCET |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.4 | TWO WAY BIB COCK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.5 | TWIN ROBE HOOK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.6 | TOILET PAPER HOLDER |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.5.7 | WASH BASIN |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.5.9 | ANGLE VALVE |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.5.11 | URINAL BASIN |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.5.13 | SOAP DISPENS ER |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.6 | 16TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 16-Oct-26 / | 18-Oct-26 / | - | 100 | 0 | 0.00%
20.6.1 | WATER CLOSET |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.3 | HEALTH FAUCET |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.4 | TWO WAY BIB COCK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.5 | TWIN ROBE HOOK |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.6 | TOILET PAPER HOLDER |  | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 0 | 0 | 0.00%
20.6.7 | WASH BASIN |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.6.9 | ANGLE VALVE |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 0 | 0 | 0.00%
20.6.11 | URINAL BASIN |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.6.13 | SOAP DISPENS ER |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 18-Oct-26 / | 18-Oct-26 / | - | 0 | 0 | 0.00%
20.7 | 16TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
20.8 | 16TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
21 | 17TH FLOOR |  | 83 days | 31-Jul-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.1 | 17TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 4 days | 25-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
21.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 12.7 | 0 | 0.00%
21.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 94 | 0 | 0.00%
21.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 2.2 | 0 | 0.00%
21.1.4 | 25 Mm Ball Valve |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 8 | 0 | 0.00%
21.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
21.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
21.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
21.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.1.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
21.2 | 17TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 34 days | 25-Aug-26 / | 27-Sep-26 / | - | 100 | 0 | 0.00%
21.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Sep-26 / | 27-Sep-26 / | - | 12.7 | 0 | 0.00%
21.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 94 | 0 | 0.00%
21.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 2.2 | 0 | 0.00%
21.2.4 | 25 Mm Ball Valve |  | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 8 | 0 | 0.00%
21.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
21.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
21.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
21.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 26-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
21.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
21.3 | 17TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 31-Jul-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
21.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 4 | 0 | 0.00%
21.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 14.28 | 0 | 0.00%
21.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 51.98 | 0 | 0.00%
21.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 9 | 0 | 0.00%
21.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 5 | 0 | 0.00%
21.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 31-Jul-26 / | 31-Jul-26 / | 7 | 5 | 0 | 0.00%
21.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | ARVIND PADHAR, PRAFULLA MALIK | 1 days | 31-Jul-26 / | 31-Jul-26 / | 7 | 17 | 0 | 0.00%
21.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
21.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
21.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
21.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
21.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
21.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
21.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
21.4 | 17TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 31-Jul-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
21.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 4 | 0 | 0.00%
21.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 14.28 | 0 | 0.00%
21.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 51.98 | 0 | 0.00%
21.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 9 | 0 | 0.00%
21.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 5 | 0 | 0.00%
21.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 31-Jul-26 / | 31-Jul-26 / | 7 | 5 | 0 | 0.00%
21.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 31-Jul-26 / | 31-Jul-26 / | 7 | 17 | 0 | 0.00%
21.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 01-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.4.11 | DRAINAG E CHASING | SUKANTA | 1 days | 03-Aug-26 / | 03-Aug-26 / | 4 | 100 | 0 | 0.00%
21.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
21.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
21.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
21.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
21.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
21.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
21.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
21.5 | 17TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 19-Oct-26 / | 21-Oct-26 / | - | 100 | 0 | 0.00%
21.5.1 | WATER CLOSET |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.3 | HEALTH FAUCET |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.4 | TWO WAY BIB COCK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.5 | TWIN ROBE HOOK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.6 | TOILET PAPER HOLDER |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.5.7 | WASH BASIN |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.5.9 | ANGLE VALVE |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.5.11 | URINAL BASIN |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.5.13 | SOAP DISPENS ER |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.6 | 17TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 19-Oct-26 / | 21-Oct-26 / | - | 100 | 0 | 0.00%
21.6.1 | WATER CLOSET |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.3 | HEALTH FAUCET |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.4 | TWO WAY BIB COCK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.5 | TWIN ROBE HOOK |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.6 | TOILET PAPER HOLDER |  | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 0 | 0 | 0.00%
21.6.7 | WASH BASIN |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.6.9 | ANGLE VALVE |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 0 | 0 | 0.00%
21.6.11 | URINAL BASIN |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.6.13 | SOAP DISPENS ER |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 21-Oct-26 / | 21-Oct-26 / | - | 0 | 0 | 0.00%
21.7 | 17TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
21.8 | 17TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
22 | 18TH FLOOR |  | 85 days | 01-Aug-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.1 | 18TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 26-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 12.7 | 0 | 0.00%
22.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 94 | 0 | 0.00%
22.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 2.2 | 0 | 0.00%
22.1.4 | 25 Mm Ball Valve |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 8 | 0 | 0.00%
22.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
22.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
22.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
22.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 100 | 0 | 0.00%
22.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 30-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 30-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 29-Aug-26 / | 29-Aug-26 / | - | 100 | 0 | 0.00%
22.2 | 18TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 26-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 12.7 | 0 | 0.00%
22.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 94 | 0 | 0.00%
22.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 2.2 | 0 | 0.00%
22.2.4 | 25 Mm Ball Valve |  | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 8 | 0 | 0.00%
22.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
22.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
22.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
22.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 28-Aug-26 / | 29-Aug-26 / | - | 100 | 0 | 0.00%
22.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 30-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 30-Aug-26 / | 30-Aug-26 / | - | 100 | 0 | 0.00%
22.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 29-Aug-26 / | 29-Aug-26 / | - | 100 | 0 | 0.00%
22.3 | 18TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 01-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
22.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 4 | 0 | 0.00%
22.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 14.28 | 0 | 0.00%
22.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 51.98 | 0 | 0.00%
22.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 9 | 0 | 0.00%
22.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 5 | 0 | 0.00%
22.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 5 | 0 | 0.00%
22.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 17 | 0 | 0.00%
22.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
22.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
22.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
22.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
22.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
22.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
22.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
22.4 | 18TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 01-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
22.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 4 | 0 | 0.00%
22.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 14.28 | 0 | 0.00%
22.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 51.98 | 0 | 0.00%
22.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 9 | 0 | 0.00%
22.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 5 | 0 | 0.00%
22.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 5 | 0 | 0.00%
22.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 01-Aug-26 / | 01-Aug-26 / | 6 | 17 | 0 | 0.00%
22.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 02-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.4.11 | DRAINAG E CHASING | SUKANTA | 1 days | 04-Aug-26 / | 04-Aug-26 / | 3 | 100 | 0 | 0.00%
22.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 05-Aug-26 / | 05-Aug-26 / | 2 | 100 | 0 | 0.00%
22.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 06-Aug-26 / | 06-Aug-26 / | 1 | 100 | 0 | 0.00%
22.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 07-Aug-26 / | 07-Aug-26 / | - | 100 | 0 | 0.00%
22.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 100 | 0 | 0.00%
22.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 09-Aug-26 / | 09-Aug-26 / | - | 100 | 0 | 0.00%
22.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 10-Aug-26 / | 10-Aug-26 / | - | 100 | 0 | 0.00%
22.4.18 | DRAINAG E LINE, LEVEL & TESTING1 | SUKANTA | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
22.5 | 18TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 22-Oct-26 / | 24-Oct-26 / | - | 100 | 0 | 0.00%
22.5.1 | WATER CLOSET |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.3 | HEALTH FAUCET |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.4 | TWO WAY BIB COCK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.5 | TWIN ROBE HOOK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.6 | TOILET PAPER HOLDER |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.5.7 | WASH BASIN |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.5.9 | ANGLE VALVE |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.5.11 | URINAL BASIN |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.5.13 | SOAP DISPENS ER |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.6 | 18TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 22-Oct-26 / | 24-Oct-26 / | - | 100 | 0 | 0.00%
22.6.1 | WATER CLOSET |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.3 | HEALTH FAUCET |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.4 | TWO WAY BIB COCK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.5 | TWIN ROBE HOOK |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.6 | TOILET PAPER HOLDER |  | 1 days | 22-Oct-26 / | 22-Oct-26 / | - | 0 | 0 | 0.00%
22.6.7 | WASH BASIN |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.6.9 | ANGLE VALVE |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 23-Oct-26 / | 23-Oct-26 / | - | 0 | 0 | 0.00%
22.6.11 | URINAL BASIN |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.6.13 | SOAP DISPENS ER |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 24-Oct-26 / | 24-Oct-26 / | - | 0 | 0 | 0.00%
22.7 | 18TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
22.8 | 18TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
23 | 19TH FLOOR |  | 81 days | 08-Aug-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.1 | 19TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 02-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 12.7 | 0 | 0.00%
23.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 94 | 0 | 0.00%
23.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 2.2 | 0 | 0.00%
23.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 8 | 0 | 0.00%
23.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
23.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
23.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 100 | 0 | 0.00%
23.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
23.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
23.2 | 19TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 02-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 12.7 | 0 | 0.00%
23.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 94 | 0 | 0.00%
23.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 2.2 | 0 | 0.00%
23.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 8 | 0 | 0.00%
23.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
23.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 02-Sep-26 / | 02-Sep-26 / | - | 100 | 0 | 0.00%
23.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 100 | 0 | 0.00%
23.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 04-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
23.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
23.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 05-Sep-26 / | 05-Sep-26 / | - | 100 | 0 | 0.00%
23.3 | 19TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 08-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
23.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 4 | 0 | 0.00%
23.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 14.28 | 0 | 0.00%
23.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 51.98 | 0 | 0.00%
23.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 9 | 0 | 0.00%
23.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 5 | 0 | 0.00%
23.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 5 | 0 | 0.00%
23.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 17 | 0 | 0.00%
23.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
23.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
23.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 14-Aug-26 / | 14-Aug-26 / | - | 100 | 0 | 0.00%
23.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 15-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
23.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
23.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
23.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 18-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
23.4 | 19TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 08-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
23.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 4 | 0 | 0.00%
23.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 14.28 | 0 | 0.00%
23.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 51.98 | 0 | 0.00%
23.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 9 | 0 | 0.00%
23.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 5 | 0 | 0.00%
23.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 5 | 0 | 0.00%
23.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 08-Aug-26 / | 08-Aug-26 / | - | 17 | 0 | 0.00%
23.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 09-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.4.11 | DRAINAG E CHASING | SUKANTA | 1 days | 11-Aug-26 / | 11-Aug-26 / | - | 100 | 0 | 0.00%
23.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 12-Aug-26 / | 12-Aug-26 / | - | 100 | 0 | 0.00%
23.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 100 | 0 | 0.00%
23.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 14-Aug-26 / | 14-Aug-26 / | - | 100 | 0 | 0.00%
23.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 15-Aug-26 / | 15-Aug-26 / | - | 100 | 0 | 0.00%
23.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
23.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
23.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 18-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
23.5 | 19TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 25-Oct-26 / | 27-Oct-26 / | - | 100 | 0 | 0.00%
23.5.1 | WATER CLOSET |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.3 | HEALTH FAUCET |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.4 | TWO WAY BIB COCK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.5 | TWIN ROBE HOOK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.6 | TOILET PAPER HOLDER |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.5.7 | WASH BASIN |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.5.9 | ANGLE VALVE |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.5.11 | URINAL BASIN |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.5.13 | SOAP DISPENS ER |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.6 | 19TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 25-Oct-26 / | 27-Oct-26 / | - | 100 | 0 | 0.00%
23.6.1 | WATER CLOSET |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.3 | HEALTH FAUCET |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.4 | TWO WAY BIB COCK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.5 | TWIN ROBE HOOK |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.6 | TOILET PAPER HOLDER |  | 1 days | 25-Oct-26 / | 25-Oct-26 / | - | 0 | 0 | 0.00%
23.6.7 | WASH BASIN |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.6.9 | ANGLE VALVE |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 0 | 0 | 0.00%
23.6.11 | URINAL BASIN |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.6.13 | SOAP DISPENS ER |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 0 | 0 | 0.00%
23.7 | 19TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
23.8 | 19TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
24 | 20TH FLOOR |  | 79 days | 13-Aug-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.1 | 20TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 5 days | 07-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 08-Sep-26 / | 09-Sep-26 / | - | 12.7 | 0 | 0.00%
24.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 08-Sep-26 / | 09-Sep-26 / | - | 94 | 0 | 0.00%
24.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 08-Sep-26 / | 09-Sep-26 / | - | 2.2 | 0 | 0.00%
24.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 08-Sep-26 / | 09-Sep-26 / | - | 8 | 0 | 0.00%
24.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
24.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
24.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 100 | 0 | 0.00%
24.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 08-Sep-26 / | 09-Sep-26 / | - | 100 | 0 | 0.00%
24.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 100 | 0 | 0.00%
24.2 | 20TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 5 days | 07-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 09-Sep-26 / | 10-Sep-26 / | - | 12.7 | 0 | 0.00%
24.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 09-Sep-26 / | 10-Sep-26 / | - | 94 | 0 | 0.00%
24.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 09-Sep-26 / | 10-Sep-26 / | - | 2.2 | 0 | 0.00%
24.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 09-Sep-26 / | 10-Sep-26 / | - | 8 | 0 | 0.00%
24.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
24.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
24.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 100 | 0 | 0.00%
24.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 09-Sep-26 / | 10-Sep-26 / | - | 100 | 0 | 0.00%
24.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
24.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 100 | 0 | 0.00%
24.3 | 20TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 13-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
24.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 4 | 0 | 0.00%
24.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 14.28 | 0 | 0.00%
24.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 51.98 | 0 | 0.00%
24.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 9 | 0 | 0.00%
24.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 5 | 0 | 0.00%
24.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 5 | 0 | 0.00%
24.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 17 | 0 | 0.00%
24.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
24.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 18-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
24.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 19-Aug-26 / | 19-Aug-26 / | - | 100 | 0 | 0.00%
24.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 20-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
24.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
24.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 22-Aug-26 / | 22-Aug-26 / | - | 100 | 0 | 0.00%
24.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
24.4 | 20TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 13-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
24.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 4 | 0 | 0.00%
24.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 14.28 | 0 | 0.00%
24.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 51.98 | 0 | 0.00%
24.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 9 | 0 | 0.00%
24.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 5 | 0 | 0.00%
24.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 5 | 0 | 0.00%
24.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 13-Aug-26 / | 13-Aug-26 / | - | 17 | 0 | 0.00%
24.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 14-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.4.11 | DRAINAG E CHASING | SUKANTA | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
24.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 100 | 0 | 0.00%
24.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 18-Aug-26 / | 18-Aug-26 / | - | 100 | 0 | 0.00%
24.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 19-Aug-26 / | 19-Aug-26 / | - | 100 | 0 | 0.00%
24.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 20-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
24.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
24.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 22-Aug-26 / | 22-Aug-26 / | - | 100 | 0 | 0.00%
24.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
24.5 | 20TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 28-Oct-26 / | 30-Oct-26 / | - | 100 | 0 | 0.00%
24.5.1 | WATER CLOSET |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.3 | HEALTH FAUCET |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.4 | TWO WAY BIB COCK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.5 | TWIN ROBE HOOK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.6 | TOILET PAPER HOLDER |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.5.7 | WASH BASIN |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.5.9 | ANGLE VALVE |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.5.11 | URINAL BASIN |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.5.13 | SOAP DISPENS ER |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.6 | 20TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 28-Oct-26 / | 30-Oct-26 / | - | 100 | 0 | 0.00%
24.6.1 | WATER CLOSET |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.3 | HEALTH FAUCET |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.4 | TWO WAY BIB COCK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.5 | TWIN ROBE HOOK |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.6 | TOILET PAPER HOLDER |  | 1 days | 28-Oct-26 / | 28-Oct-26 / | - | 0 | 0 | 0.00%
24.6.7 | WASH BASIN |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.6.9 | ANGLE VALVE |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 29-Oct-26 / | 29-Oct-26 / | - | 0 | 0 | 0.00%
24.6.11 | URINAL BASIN |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.6.13 | SOAP DISPENS ER |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
24.7 | 20TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
24.8 | 20TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
25 | 21ST FLOOR |  | 80 days | 16-Aug-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.1 | 21ST FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 32 days | 16-Aug-26 / | 16-Sep-26 / | - | 100 | 0 | 0.00%
25.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 12.7 | 0 | 0.00%
25.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 94 | 0 | 0.00%
25.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 2.2 | 0 | 0.00%
25.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 8 | 0 | 0.00%
25.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
25.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
25.1.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
25.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 100 | 0 | 0.00%
25.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 16-Aug-26 / | 16-Aug-26 / | - | 100 | 0 | 0.00%
25.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 100 | 0 | 0.00%
25.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 100 | 0 | 0.00%
25.2 | 21ST FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 11-Sep-26 / | 16-Sep-26 / | - | 100 | 0 | 0.00%
25.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 12.7 | 0 | 0.00%
25.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 94 | 0 | 0.00%
25.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 2.2 | 0 | 0.00%
25.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 8 | 0 | 0.00%
25.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
25.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
25.2.7 | WATER SUPPLY CHASING | APURBA BISWAS | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
25.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 13-Sep-26 / | 14-Sep-26 / | - | 100 | 0 | 0.00%
25.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 100 | 0 | 0.00%
25.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 16-Sep-26 / | 16-Sep-26 / | - | 100 | 0 | 0.00%
25.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 15-Sep-26 / | 15-Sep-26 / | - | 100 | 0 | 0.00%
25.3 | 21ST FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 12 days | 17-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
25.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 4 | 0 | 0.00%
25.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 14.28 | 0 | 0.00%
25.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 51.98 | 0 | 0.00%
25.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 9 | 0 | 0.00%
25.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 5 | 0 | 0.00%
25.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 5 | 0 | 0.00%
25.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 17 | 0 | 0.00%
25.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
25.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
25.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
25.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
25.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 22-Aug-26 / | 22-Aug-26 / | - | 100 | 0 | 0.00%
25.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
25.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 24-Aug-26 / | 24-Aug-26 / | - | 100 | 0 | 0.00%
25.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
25.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
25.3.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
25.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
25.4 | 21ST FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 12 days | 17-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
25.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 4 | 0 | 0.00%
25.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 14.28 | 0 | 0.00%
25.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 51.98 | 0 | 0.00%
25.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 9 | 0 | 0.00%
25.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 5 | 0 | 0.00%
25.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 5 | 0 | 0.00%
25.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 17-Aug-26 / | 17-Aug-26 / | - | 17 | 0 | 0.00%
25.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
25.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 18-Aug-26 / | 20-Aug-26 / | - | 100 | 0 | 0.00%
25.4.10 | DRAINAG E JARI MARKING 1 | SUKANTA | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
25.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 21-Aug-26 / | 21-Aug-26 / | - | 100 | 0 | 0.00%
25.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 22-Aug-26 / | 22-Aug-26 / | - | 100 | 0 | 0.00%
25.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 23-Aug-26 / | 23-Aug-26 / | - | 100 | 0 | 0.00%
25.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 24-Aug-26 / | 24-Aug-26 / | - | 100 | 0 | 0.00%
25.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 25-Aug-26 / | 25-Aug-26 / | - | 100 | 0 | 0.00%
25.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 26-Aug-26 / | 26-Aug-26 / | - | 100 | 0 | 0.00%
25.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 27-Aug-26 / | 27-Aug-26 / | - | 100 | 0 | 0.00%
25.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 28-Aug-26 / | 28-Aug-26 / | - | 100 | 0 | 0.00%
25.5 | 21ST FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 01-Nov-26 / | 03-Nov-26 / | - | 100 | 0 | 0.00%
25.5.1 | WATER CLOSET |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.3 | HEALTH FAUCET |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.4 | TWO WAY BIB COCK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.5 | TWIN ROBE HOOK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.6 | TOILET PAPER HOLDER |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.5.7 | WASH BASIN |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.5.9 | ANGLE VALVE |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.5.11 | URINAL BASIN |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.5.13 | SOAP DISPENS ER |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.6 | 21ST FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 01-Nov-26 / | 03-Nov-26 / | - | 100 | 0 | 0.00%
25.6.1 | WATER CLOSET |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.3 | HEALTH FAUCET |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.4 | TWO WAY BIB COCK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.5 | TWIN ROBE HOOK |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.6 | TOILET PAPER HOLDER |  | 1 days | 01-Nov-26 / | 01-Nov-26 / | - | 0 | 0 | 0.00%
25.6.7 | WASH BASIN |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.6.9 | ANGLE VALVE |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 02-Nov-26 / | 02-Nov-26 / | - | 0 | 0 | 0.00%
25.6.11 | URINAL BASIN |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.6.13 | SOAP DISPENS ER |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 03-Nov-26 / | 03-Nov-26 / | - | 0 | 0 | 0.00%
25.7 | 21ST FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
25.8 | 21ST FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
26 | 22ND FLOOR |  | 65 days | 03-Sep-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.1 | 22TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 28-Sep-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 12.7 | 0 | 0.00%
26.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 94 | 0 | 0.00%
26.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 2.2 | 0 | 0.00%
26.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 8 | 0 | 0.00%
26.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 100 | 0 | 0.00%
26.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 100 | 0 | 0.00%
26.1.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 100 | 0 | 0.00%
26.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 100 | 0 | 0.00%
26.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 100 | 0 | 0.00%
26.2 | 22TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 28-Sep-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 12.7 | 0 | 0.00%
26.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 94 | 0 | 0.00%
26.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 2.2 | 0 | 0.00%
26.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 8 | 0 | 0.00%
26.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 100 | 0 | 0.00%
26.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 100 | 0 | 0.00%
26.2.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 100 | 0 | 0.00%
26.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 30-Sep-26 / | 01-Oct-26 / | - | 100 | 0 | 0.00%
26.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 03-Oct-26 / | 03-Oct-26 / | - | 100 | 0 | 0.00%
26.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 02-Oct-26 / | 02-Oct-26 / | - | 100 | 0 | 0.00%
26.3 | 22TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 03-Sep-26 / | 13-Sep-26 / | - | 100 | 0 | 0.00%
26.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 4 | 0 | 0.00%
26.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 14.28 | 0 | 0.00%
26.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 51.98 | 0 | 0.00%
26.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 9 | 0 | 0.00%
26.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 5 | 0 | 0.00%
26.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 5 | 0 | 0.00%
26.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 17 | 0 | 0.00%
26.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
26.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 100 | 0 | 0.00%
26.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 100 | 0 | 0.00%
26.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 100 | 0 | 0.00%
26.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
26.3.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
26.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 100 | 0 | 0.00%
26.4 | 22TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 03-Sep-26 / | 13-Sep-26 / | - | 100 | 0 | 0.00%
26.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 4 | 0 | 0.00%
26.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 14.28 | 0 | 0.00%
26.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 51.98 | 0 | 0.00%
26.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 9 | 0 | 0.00%
26.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 5 | 0 | 0.00%
26.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 5 | 0 | 0.00%
26.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 03-Sep-26 / | 03-Sep-26 / | - | 17 | 0 | 0.00%
26.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 04-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 06-Sep-26 / | 06-Sep-26 / | - | 100 | 0 | 0.00%
26.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 07-Sep-26 / | 07-Sep-26 / | - | 100 | 0 | 0.00%
26.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 08-Sep-26 / | 08-Sep-26 / | - | 100 | 0 | 0.00%
26.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 09-Sep-26 / | 09-Sep-26 / | - | 100 | 0 | 0.00%
26.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 10-Sep-26 / | 10-Sep-26 / | - | 100 | 0 | 0.00%
26.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 11-Sep-26 / | 11-Sep-26 / | - | 100 | 0 | 0.00%
26.4.17 | DRAINAG E JARI REFILLIN G | MANOJ | 1 days | 12-Sep-26 / | 12-Sep-26 / | - | 100 | 0 | 0.00%
26.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 13-Sep-26 / | 13-Sep-26 / | - | 100 | 0 | 0.00%
26.5 | 22THFLO OR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 04-Nov-26 / | 06-Nov-26 / | - | 100 | 0 | 0.00%
26.5.1 | WATER CLOSET |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.3 | HEALTH FAUCET |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.4 | TWO WAY BIB COCK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.5 | TWIN ROBE HOOK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.6 | TOILET PAPER HOLDER |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.5.7 | WASH BASIN |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.5.9 | ANGLE VALVE |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.5.11 | URINAL BASIN |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.5.13 | SOAP DISPENS ER |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.6 | 22TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 04-Nov-26 / | 06-Nov-26 / | - | 100 | 0 | 0.00%
26.6.1 | WATER CLOSET |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.3 | HEALTH FAUCET |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.4 | TWO WAY BIB COCK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.5 | TWIN ROBE HOOK |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.6 | TOILET PAPER HOLDER |  | 1 days | 04-Nov-26 / | 04-Nov-26 / | - | 0 | 0 | 0.00%
26.6.7 | WASH BASIN |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.6.9 | ANGLE VALVE |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 05-Nov-26 / | 05-Nov-26 / | - | 0 | 0 | 0.00%
26.6.11 | URINAL BASIN |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.6.13 | SOAP DISPENS ER |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 06-Nov-26 / | 06-Nov-26 / | - | 0 | 0 | 0.00%
26.7 | 22TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
26.8 | 22TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
27 | 23TH FLOOR |  | 51 days | 20-Sep-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.1 | 23TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 15-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 12.7 | 0 | 0.00%
27.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 94 | 0 | 0.00%
27.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 2.2 | 0 | 0.00%
27.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 8 | 0 | 0.00%
27.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
27.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
27.1.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 100 | 0 | 0.00%
27.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 100 | 0 | 0.00%
27.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 100 | 0 | 0.00%
27.2 | 23TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 15-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 12.7 | 0 | 0.00%
27.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 94 | 0 | 0.00%
27.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 2.2 | 0 | 0.00%
27.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 8 | 0 | 0.00%
27.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
27.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
27.2.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 100 | 0 | 0.00%
27.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 17-Oct-26 / | 18-Oct-26 / | - | 100 | 0 | 0.00%
27.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.2.10 | WATERSU PPLY JARI REFILNG | MANOJ | 1 days | 20-Oct-26 / | 20-Oct-26 / | - | 100 | 0 | 0.00%
27.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 19-Oct-26 / | 19-Oct-26 / | - | 100 | 0 | 0.00%
27.3 | 23TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 20-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
27.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 4 | 0 | 0.00%
27.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 14.28 | 0 | 0.00%
27.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 51.98 | 0 | 0.00%
27.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 9 | 0 | 0.00%
27.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 5 | 0 | 0.00%
27.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 5 | 0 | 0.00%
27.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 17 | 0 | 0.00%
27.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.3.11 | DRAINAG E CHASING | MANOJ | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 100 | 0 | 0.00%
27.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 100 | 0 | 0.00%
27.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 100 | 0 | 0.00%
27.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 100 | 0 | 0.00%
27.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 28-Sep-26 / 03-Aug-26 | 28-Sep-26 / | - | 100 | 0 | 0.00%
27.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 100 | 0 | 0.00%
27.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
27.4 | 23TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 20-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
27.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 4 | 0 | 0.00%
27.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 14.28 | 0 | 0.00%
27.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 51.98 | 0 | 0.00%
27.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 9 | 0 | 0.00%
27.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 5 | 0 | 0.00%
27.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 5 | 0 | 0.00%
27.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 20-Sep-26 / | 20-Sep-26 / | - | 17 | 0 | 0.00%
27.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 21-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.4.11 | DRAINAG E CHASING | MANOJ | 1 days | 23-Sep-26 / | 23-Sep-26 / | - | 100 | 0 | 0.00%
27.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 24-Sep-26 / | 24-Sep-26 / | - | 100 | 0 | 0.00%
27.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 25-Sep-26 / | 25-Sep-26 / | - | 100 | 0 | 0.00%
27.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 26-Sep-26 / | 26-Sep-26 / | - | 100 | 0 | 0.00%
27.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 27-Sep-26 / | 27-Sep-26 / | - | 100 | 0 | 0.00%
27.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 28-Sep-26 / | 28-Sep-26 / | - | 100 | 0 | 0.00%
27.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 29-Sep-26 / | 29-Sep-26 / | - | 100 | 0 | 0.00%
27.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 30-Sep-26 / | 30-Sep-26 / | - | 100 | 0 | 0.00%
27.5 | 23TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 07-Nov-26 / | 09-Nov-26 / | - | 100 | 0 | 0.00%
27.5.1 | WATER CLOSET |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.3 | HEALTH FAUCET |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.4 | TWO WAY BIB COCK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.5 | TWIN ROBE HOOK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.6 | TOILET PAPER HOLDER |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.5.7 | WASH BASIN |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.5.9 | ANGLE VALVE |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.5.11 | URINAL BASIN |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.5.13 | SOAP DISPENS ER |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.6 | 23TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 07-Nov-26 / | 09-Nov-26 / | - | 100 | 0 | 0.00%
27.6.1 | WATER CLOSET |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.3 | HEALTH FAUCET |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.4 | TWO WAY BIB COCK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.5 | TWIN ROBE HOOK |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.6 | TOILET PAPER HOLDER |  | 1 days | 07-Nov-26 / | 07-Nov-26 / | - | 0 | 0 | 0.00%
27.6.7 | WASH BASIN |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.6.9 | ANGLE VALVE |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 08-Nov-26 / | 08-Nov-26 / | - | 0 | 0 | 0.00%
27.6.11 | URINAL BASIN |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.6.13 | SOAP DISPENS ER |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 09-Nov-26 / | 09-Nov-26 / | - | 0 | 0 | 0.00%
27.7 | 23TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
27.8 | 23TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
28 | 24TH FLOOR |  | 37 days | 07-Oct-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.1 | 24TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 6 days | 26-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.1.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 12.7 | 0 | 0.00%
28.1.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 94 | 0 | 0.00%
28.1.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 2.2 | 0 | 0.00%
28.1.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 8 | 0 | 0.00%
28.1.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 100 | 0 | 0.00%
28.1.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 100 | 0 | 0.00%
28.1.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 100 | 0 | 0.00%
28.1.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 100 | 0 | 0.00%
28.1.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 31-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.1.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 31-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.1.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 100 | 0 | 0.00%
28.2 | 24TH FLOOR WATER SUPPLY FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 6 days | 26-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.2.1 | 20 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 12.7 | 0 | 0.00%
28.2.2 | 25 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 94 | 0 | 0.00%
28.2.3 | 40 MM PIPE-SDR 11 5M ASTRAL CPVC | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 2.2 | 0 | 0.00%
28.2.4 | 25 Mm Ball Valve | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 8 | 0 | 0.00%
28.2.5 | FASTNER ROD AND HANGER S FIXING | APURBA BISWAS | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 100 | 0 | 0.00%
28.2.6 | WATER SUPPLY JARI MARKING | APURBA BISWAS | 1 days | 26-Oct-26 / | 26-Oct-26 / | - | 100 | 0 | 0.00%
28.2.7 | WATER SUPPLY CHASING | MANOJ | 1 days | 27-Oct-26 / | 27-Oct-26 / | - | 100 | 0 | 0.00%
28.2.8 | WATERSU PPLY HANGING LINE | APURBA BISWAS | 2 days | 28-Oct-26 / | 29-Oct-26 / | - | 100 | 0 | 0.00%
28.2.9 | WATERSU PPLY CONCEAL LINE | APURBA BISWAS | 1 days | 31-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.2.10 | WATERSU PPLY JARI REFILNG | APURBA BISWAS | 1 days | 31-Oct-26 / | 31-Oct-26 / | - | 100 | 0 | 0.00%
28.2.11 | WATER SUPPLY LINE, LEVEL & TESTING | APURBA BISWAS | 1 days | 30-Oct-26 / | 30-Oct-26 / | - | 100 | 0 | 0.00%
28.3 | 24TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 11 days | 07-Oct-26 / | 17-Oct-26 / | - | 100 | 0 | 0.00%
28.3.1 | 110MM PVC CLEANOU T PLUG | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 4 | 0 | 0.00%
28.3.2 | 50MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 14.28 | 0 | 0.00%
28.3.3 | 110MM PVC SWR TYPE-B SELFIT | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 51.98 | 0 | 0.00%
28.3.4 | 110 X 110MM P- TRAP | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 9 | 0 | 0.00%
28.3.5 | SELFIT SWR TYPE-B HIGHRISE R | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 5 | 0 | 0.00%
28.3.6 | EAST SIDE CORE CUTTING 77MM x 150MM | PRAFULLA MALIK | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 5 | 0 | 0.00%
28.3.7 | EAST SIDE CORE CUTTING 125MM x 175MM | PRAFULLA MALIK | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 17 | 0 | 0.00%
28.3.8 | SOIL LINE HANGING | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.3.9 | WASTE LINE HANGING | PRAFULLA MALIK | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.3.10 | DRAINAG E JARI MARKING | PRAFULLA MALIK | 1 days | 10-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.3.11 | DRAINAG E CHASING | PRAFULLA MALIK | 1 days | 10-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.3.12 | WASHBA SIN OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 11-Oct-26 / | 11-Oct-26 / | - | 100 | 0 | 0.00%
28.3.13 | URINAL OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 12-Oct-26 / | 12-Oct-26 / | - | 100 | 0 | 0.00%
28.3.14 | WC OUTLET CONNEC TION | PRAFULLA MALIK | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 100 | 0 | 0.00%
28.3.15 | FLUSH TANK FIXING | PRAFULLA MALIK | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 100 | 0 | 0.00%
28.3.16 | URINAL SENSOR FIXING | PRAFULLA MALIK | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
28.3.17 | DRAINAG E JARI REFILLIN G | PRAFULLA MALIK | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 100 | 0 | 0.00%
28.3.18 | DRAINAG E LINE, LEVEL & TESTING | PRAFULLA MALIK | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 100 | 0 | 0.00%
28.4 | 24TH FLOOR DRAINAG E FOR MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 11 days | 07-Oct-26 / | 17-Oct-26 / | - | 100 | 0 | 0.00%
28.4.1 | 110MM PVC CLEANOU T PLUG | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 4 | 0 | 0.00%
28.4.2 | 50MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 14.28 | 0 | 0.00%
28.4.3 | 110MM PVC SWR TYPE-B SELFIT | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 51.98 | 0 | 0.00%
28.4.4 | 110 X 110MM P- TRAP | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 9 | 0 | 0.00%
28.4.5 | SELFIT SWR TYPE-B HIGHRISE R | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 5 | 0 | 0.00%
28.4.6 | WEST SIDE CORE CUTTING 77MM x 150MM | SUKANTA | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 5 | 0 | 0.00%
28.4.7 | WEST SIDE CORE CUTTING 125MM x 175MM | SUKANTA | 1 days | 07-Oct-26 / | 07-Oct-26 / | - | 17 | 0 | 0.00%
28.4.8 | SOIL LINE HANGING | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.4.9 | WASTE LINE HANGING | SUKANTA | 3 days | 08-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.4.10 | DRAINAG E JARI MARKING | SUKANTA | 1 days | 10-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.4.11 | DRAINAG E CHASING | SUKANTA | 1 days | 10-Oct-26 / | 10-Oct-26 / | - | 100 | 0 | 0.00%
28.4.12 | WASHBA SIN OUTLET CONNEC TION | SUKANTA | 1 days | 11-Oct-26 / | 11-Oct-26 / | - | 100 | 0 | 0.00%
28.4.13 | URINAL OUTLET CONNEC TION | SUKANTA | 1 days | 12-Oct-26 / | 12-Oct-26 / | - | 100 | 0 | 0.00%
28.4.14 | WC OUTLET CONNEC TION | SUKANTA | 1 days | 13-Oct-26 / | 13-Oct-26 / | - | 100 | 0 | 0.00%
28.4.15 | FLUSH TANK FIXING | SUKANTA | 1 days | 14-Oct-26 / | 14-Oct-26 / | - | 100 | 0 | 0.00%
28.4.16 | URINAL SENSOR FIXING | SUKANTA | 1 days | 15-Oct-26 / | 15-Oct-26 / | - | 100 | 0 | 0.00%
28.4.17 | DRAINAG E JARI REFILLIN G | SUKANTA | 1 days | 16-Oct-26 / | 16-Oct-26 / | - | 100 | 0 | 0.00%
28.4.18 | DRAINAG E LINE, LEVEL & TESTING | SUKANTA | 1 days | 17-Oct-26 / | 17-Oct-26 / | - | 100 | 0 | 0.00%
28.5 | 24TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 3 days | 10-Nov-26 / | 12-Nov-26 / | - | 100 | 0 | 0.00%
28.5.1 | WATER CLOSET |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.2 | CONSEAL ED FLUST TANK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.3 | HEALTH FAUCET |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.4 | TWO WAY BIB COCK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.5 | TWIN ROBE HOOK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.6 | TOILET PAPER HOLDER |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.5.7 | WASH BASIN |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.5.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.5.9 | ANGLE VALVE |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.5.10 | HANDICA PPED TOILET & SHOWER |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.5.11 | URINAL BASIN |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.5.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.5.13 | SOAP DISPENS ER |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.5.14 | SS SINGLE PIECE GRATING |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.6 | 24TH FLOOR CP- SANITARY FIXING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 3 days | 10-Nov-26 / | 12-Nov-26 / | - | 100 | 0 | 0.00%
28.6.1 | WATER CLOSET |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.2 | CONSEAL ED FLUSH TANK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.3 | HEALTH FAUCET |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.4 | TWO WAY BIB COCK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.5 | TWIN ROBE HOOK |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.6 | TOILET PAPER HOLDER |  | 1 days | 10-Nov-26 / | 10-Nov-26 / | - | 0 | 0 | 0.00%
28.6.7 | WASH BASIN |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.6.8 | SINGLE LEVER BASIN MIXER/PI LLAR COCK |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.6.9 | ANGLE VALVE |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.6.10 | HANDICA PPED TOILER & SHOWER |  | 1 days | 11-Nov-26 / | 11-Nov-26 / | - | 0 | 0 | 0.00%
28.6.11 | URINAL BASIN |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.6.12 | URINAL FLUSHIN G SYSTEM |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.6.13 | SOAP DISPENS ER |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.6.14 | SS SINGLE PIECE GRATING |  | 1 days | 12-Nov-26 / | 12-Nov-26 / | - | 0 | 0 | 0.00%
28.7 | 24TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET EAST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
28.8 | 24TH FLOOR CHECKIN G,HAND- OVER,CO MMISSIO NING MENS,WO MENS,AC C,EXECU TIVE TOILET WEST SIDE |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
29 | 24TH TERRACE |  |  | / | / | - | 0 | 0 | 0.00%
29.1 | TERRACE LOOPING |  |  | / | / | 45874 | 0 | 0 | 0.00%
29.2 | FLUSHIN G TANK INTER CONNEC TION |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
29.3 | DOMESTI C TANK INTER CONNEC TION |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
29.4 | TOP TERRACE WORK |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
30 | ALL FLOOR CP SANITARY |  | 76 days | 01-Sep-26 / | 15-Nov-26 / | - | 0 | 0 | 0.00%
30.1 | 1st,2nd,3r d, 4th, 5th floor all toilet cp sanitary |  | 15 days | 01-Sep-26 / | 15-Sep-26 / | - | 0 | 0 | 0.00%
30.2 | 6th,7th,8th ,9th,10th floor all toilet cp sanitary |  | 15 days | 16-Sep-26 / | 30-Sep-26 / | - | 0 | 0 | 0.00%
30.3 | 11th,12th,1 3th,14th,1 5th floor all toilet cp sanitary |  | 15 days | 01-Oct-26 / | 15-Oct-26 / | - | 0 | 0 | 0.00%
30.4 | 16th,17th, 18th,19th, 20th floor all toilet cp sanitary |  | 15 days | 16-Oct-26 / | 30-Oct-26 / | - | 0 | 0 | 0.00%
30.5 | 21,22,23,2 4th floor all toilet cp sanitary |  | 15 days | 01-Nov-26 / | 15-Nov-26 / | - | 0 | 0 | 0.00%
31 | SHAFT VERTICAL LINE |  |  | / | / | - | 0 | 0 | 0.00%
31.1 | Shaft vertical line shaft- 1,2,3,4,5,6 ,7,8,1A,8A . B-1 to 24th floor |  | 133 days | / | / | - | 0 | 0 | 0.00%
31.1.1 | PLUMBIN G SHAFT NO - 1 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.2 | PLUMBIN G SHAFT NO - 2 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.3 | PLUMBIN G SHAFT NO - 3 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.4 | PLUMBIN G SHAFT NO - 4 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.5 | PLUMBIN G SHAFT NO - 5 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.6 | PLUMBIN G SHAFT NO - 6 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.7 | PLUMBIN G SHAFT NO - 7 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.8 | PLUMBIN G SHAFT NO - 8 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.9 | PLUMBIN G SHAFT NO - 1A |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.1.10 | PLUMBIN G SHAFT NO - 8A |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2 | RWP Shaft Vertical line shaft no- 1,2,3,4,5,6 ,7,8 . B-1 to 24th floor |  | 83 days | / | / | - | 0 | 0 | 0.00%
31.2.1 | RWP SHAFT NO - 1 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.2 | RWP SHAFT NO - 2 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.3 | RWP SHAFT NO - 3 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.4 | RWP SHAFT NO - 4 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.5 | RWP SHAFT NO - 5 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.6 | RWP SHAFT NO - 6 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.7 | RWP SHAFT NO - 7 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%
31.2.8 | RWP SHAFT NO - 8 |  | 1 days | / | / | 45874 | 100 | 0 | 0.00%