## Sheet1
date | name | user-status | absent reason | number | task | start | end | delay time | task-status | reason | managerName | manager mobile
2026-08-11 | chauhan Rohit | accept |  | 7698489304 | get titl-feedback | 9:00am | 12:30pm | 10min | completed |  | chauhan rohit | 7698489306
[5 empty] | TIltva Give ppt and pdf | 1:30pm | 3:00pm |  | pending
[5 empty] | complete the delpoyment of tilt and 3m | 6:10pm | 7:31pm |  | in progress
| Jeet bhavsar | accept |  | 7490039925 | Improve quality of POST-genuis | 10:30am | 12:30pm |  | completed |  | Nidhish | 9016050336
[5 empty] | Testing and update Post Genious, Task 1 Dynamic Image Prompt & Music Library: | 1:30pm | 3:30pm |  | pending
[5 empty] | Aaram(only suvanu) | 3:40pm | 5:00pm |  | completed
[5 empty] | Engine Deployment | 5:00pm | 6:00pm |  | hold
| jay prajapati | accept |  | 9737461201 | send 100 mail to client | 10:30am | 12:30pm |  | in progress |  | Nidhish | 9016050336
[5 empty] | schedule 2-3 meeting with sir | 1:30pm | 3:00pm |  | completed
[5 empty] | meeting with nidhish sir at 6:25pm | 3:15pm | 7:05pm |  | in progress
| Poojan soni | accept |  | 9638796269 | UI refiment | 10:30am | 12:30pm |  | remark | previous list remaining | Nidhish | 9016050336
[5 empty] | Help in testing, Check with QA team | 1:30pm | 4:00pm |  | completed
[5 empty] | Do Testing | 4:00pm | 7:00pm |  | hold
| Om prajapati | accept |  | 8734848783 | optimasation | 10:30am | 12:30pm | 15min | remark | I will work tommorrow | Nidhish | 9016050336
[5 empty] | Feed Data and do end to end test | 1:30pm | 3:30pm |  | completed
[5 empty] | testing and bug fixing | 4:10pm | 6:00pm |  | pending
[5 empty] | Understand existing process and come up with plan to improve | 6:03pm | 7:00pm |  | remark | this is not my task
| Vivek mesuriya | accept |  | 7874510328 | Akash Deployment: | 10:30am | 12:30pm |  | completed |  | Nidhish | 9016050336
[5 empty] | On Borad Employees | 1:30pm | 3:30pm |  | pending
[5 empty] | Testing and Report in Group and make employee on board today | 4:00pm | 4:40pm |  | remark | not well
[5 empty] | Dr Q End to End Demo Using Omi | 5:00pm | 6:10pm |  | completed
[5 empty] | Dr Q Push notification and configurable, Reminder | 6:20pm | 7:50pm |  | blocked | not have specific instrument
| Rohit Hadiya | decline | I'm goging to village | 8320972746 | Give KT document to BCM | 10:30am | 12:30pm |  | cancelled |  | Nidhish | 9016050336
[5 empty] | Phone AI Strip Sub Account testing | 1:30pm | 4:00pm |  | cancelled
[5 empty] | Phone AI End to end Testing | 4:20pm | 7:00pm |  | cancelled
| Aayush patel | remainng |  | 8780781261 | n8n testing | 10:30am | 12:30pm |  | not send |  | Nidhish | 9016050336
[5 empty] | find bug from aakash agro | 1:30pm | 3:30pm |  | not send
[5 empty] | learn something from youtube | 4:00pm | 7:00pm |  | not send